## Paniel de Navegação
Navigation Panel
Instructions
Implementation Report
Status Report
Rundown
Staff
Daily Execution
Closing Report

## Instruções
After the Result Cell Implementation Report is formulated and the Cell implementation is defined, the Process Monitoring step shall be initiated. Therefore, the items below must be filled out:
Necessary Information for the Monitoring Process Implementation
Fill the next cell with Cell Title - Process and Area, if applicable (Ex. Piping Assembly) |  | The Cell Title must be filled out!
Fill the next cell with Cell No. |  | Cell No. must be filled out!
Fill the next cell with Rundown Start (day/month/year) |  | The Rundown Start must be filled out!
Fill the next cell with Rundown Finish (day/month/year) |  | The Rundown Finish must be filled out!
Fill the next cell with Start Week (Ex. W150) |  | If the field is empty, W1 will be considered as first week
Fill the next cell with Measurement Unit (Ex. MH, Ton) |  | Measurement Unit must be filled out!
Fill columns F, G and H of "Rundown" tab, when having values (Planned Weekly Production, Actual Weekly Production and Projected Weekly Production) | Rundown
Fill columns C, D, E, F, G and H of "Staff" tab, when having values (Planned Effective, Actual Effective, Planned Foreman, Actual Foreman) | Staff
Paste photos and fill out the name of the responsible for monitoring on "Weekly Status Report" tab | Status Report
Information for the "Status Report" elaboration - WEEKLY UPDATES
Fill the next cell with Current Week (Ex. W150) |  | Report Week must be filled out!
Update columns G and H of "Rundown" tab (Actual Weekly Production and Projected Weekly Production) | Rundown
Update columns D and F of "Staff" tab (Actual Effective e Actual Foreman) | Staff
Update Process Improvement Action Plan with Action Actual/Projected Date (column G of "Weekly Status Report" tab) and its Status (column I of "Weekly Status Report" tab). If necessary, include new actions not contemplated in the Implementation Report. | Status Report
At the end, it is possible to print the report in A3 format, the margins are set up to this format. | Status Report
Print the spreedsheet "Daily Execution" and fill column E with the daily quantitative of the following week at the execution location. | Daily Execution
Information for the "Closing Report" elaboration
Fill the next cell with Cell Closing Date (day/month/year) |  | Cell Closing Date must be filled out!
Fill the lessons learned related to external and internal problems, as well as the main solutions provided. | Closing Report
Navigation Panel

## Relatório de Implantação
Implementation Report - Result Cell | [6 empty] | Manager:
Buyer Manager:
Seller Manager:
ACTIVITY/FRONT: |  |  |  | Date: | ___/___/____ |  | Responsible:
1. PROCESS DIAGNOSIS |  |  |  |  | 3. PROCESS STATUS
Qualify Problems |  | YES | NO | Causes
EXTERNAL | Is there lack of applicatoin or consumption materials?
Are there Liberations/PT/PTT delayed?
Are there problems in the Executive Design (erros/interferences/omissions)?
Are there executive procedures missing?
Are there cranes missing?
Are there schedule informations missing (quantitative, responsible etc)?
INTERNAL | Can area layout be improved?
Are there obstacles in people or materials moving?
Do scaffolds need improvement?
Do scaffolds need assembly?
Are there tools/equipment to supply the whole team missing?
Are there problems related to HSE?
Is the current team insufficient to reach production goal?
Are there flaws in communicating the executive procedures?
| Do reworks occur? |  |  |  | 4. ACTION PLAN TO PROCESS IMPROVEMENT
[5 empty] | Action Planning Date | Action |  | Planned Date | Goal | Responsible
General Total: |  | 0 | 0
| External Total: | 0 | 0
| Internal Total: | 0 | 0
2. Activity Analisys
Main Impacts
Navigation Panel

## Relatório de Status
|  | Status Report - | [9 empty] | Updated on: |  | 2024-04-30
Start: | 0
Week
Finish: | 0 | Cell No.
[12 empty] | WX | to | WY
Rundown Curve: | [7 empty] | Rundown Table:
Cell Title | [7 empty] | Cell Title
[8 empty] | Week |  | Week Production |  | Remaining Balance
[10 empty] | Plan | Actual | Plan | Actual | Projected
Average Execution:
Historic (3 last weeks)
Projected (next 4 weeks)
Staff of the week:
[8 empty] | No. of Workers |  | Planned | Actual | MH | Planned | Actual
[8 empty] | Staff |  | 0 | 0 | Staff | 0 | 0
[8 empty] | Foreman |  | 0 | 0
Action Plan to Process Improvement | [7 empty] | Responsáveis
Action Planning Date | Action |  | Date |  | Goal | Status | Responsible
|  |  | Planned | Actual/Projected |  |  |  |  | Buyer |  |  | Seller
[9 empty] | Responsible Name |  |  | Responsible Name
RESPONSIBLE PICTURE
RESPONSIBLE PICTURE
Navigation Panel

## Realização Diária
Daily Execution -
Cell Title | Daily Quantitative [] | Rundown
| Date | Actual []
| Previous Accumulated - until |  | Total Scope
First Day
| Second Day |  | 0
Third Day
Fourth Day
Fifith Day
Sixth Day
| Seventh Day |  | Execution Goal in
| Week Accumulated Total | 0
Accumulated General - until
Navigation Panel

## Rundown
Rundown Curve -
| Week Start Day | Week |  | Weekly Production - |  |  |  | Remaining Balance -
|  |  |  | Plan | Actual | Projected | Accumulated Actual | Plan | Actual | Projected
W1 | 0 |  | W1 |  |  |  | 0 | 0 | #N/A | #N/A
[7 empty] | #N/A | #N/A | #N/A | #N/A
[7 empty] | #N/A | #N/A | #N/A | #N/A
[7 empty] | #N/A | #N/A | #N/A | #N/A
[7 empty] | #N/A | #N/A | #N/A | #N/A
[7 empty] | #N/A | #N/A | #N/A | #N/A
[7 empty] | #N/A | #N/A | #N/A | #N/A
[7 empty] | #N/A | #N/A | #N/A | #N/A
[7 empty] | #N/A | #N/A | #N/A | #N/A
[7 empty] | #N/A | #N/A | #N/A | #N/A
[7 empty] | #N/A | #N/A | #N/A | #N/A
[7 empty] | #N/A | #N/A | #N/A | #N/A
[7 empty] | #N/A | #N/A | #N/A | #N/A
[7 empty] | #N/A | #N/A | #N/A | #N/A
[7 empty] | #N/A | #N/A | #N/A | #N/A
[7 empty] | #N/A | #N/A | #N/A | #N/A
[7 empty] | #N/A | #N/A | #N/A | #N/A
[7 empty] | #N/A | #N/A | #N/A | #N/A
[7 empty] | #N/A | #N/A | #N/A | #N/A
[7 empty] | #N/A | #N/A | #N/A | #N/A
[7 empty] | #N/A | #N/A | #N/A | #N/A
[7 empty] | #N/A | #N/A | #N/A | #N/A
[7 empty] | #N/A | #N/A | #N/A | #N/A
[7 empty] | #N/A | #N/A | #N/A | #N/A
[7 empty] | #N/A | #N/A | #N/A | #N/A
[7 empty] | #N/A | #N/A | #N/A | #N/A
[7 empty] | #N/A | #N/A | #N/A | #N/A
[7 empty] | #N/A | #N/A | #N/A | #N/A
[7 empty] | #N/A | #N/A | #N/A | #N/A
[7 empty] | #N/A | #N/A | #N/A | #N/A
[7 empty] | #N/A | #N/A | #N/A | #N/A
[7 empty] | #N/A | #N/A | #N/A | #N/A
[7 empty] | #N/A | #N/A | #N/A | #N/A
[7 empty] | #N/A | #N/A | #N/A | #N/A
[7 empty] | #N/A | #N/A | #N/A | #N/A
[7 empty] | #N/A | #N/A | #N/A | #N/A
Navigation Panel

## Efetivo
Staff Counting -
|  | Staff - No. of Workers |  | Staff - MH |  | No. of Foremen
Week Start Day | Week | Planned | Actual | Planned | Actual | Planned | Actual
0 | W1
Navigation Panel

## Encerramento
|  | Closing Report - | [9 empty] | Cell Closed on: |  | 0
Start: | 0
Planned Date:
Finish: | 0 | Cell No.
Actual Date:
Rundown Curve: | [7 empty] | Production and Productivity Table:
() | [7 empty] | Cell Title |  |  |  | (mh/unit)
Production
Daily Average
[12 empty] | Plan | Actual
[8 empty] | Weekly Average |  | 0
[8 empty] | Total |  | 0
[8 empty] | Average Staff: |  |  |  | Total Staff:
[8 empty] | No. Workers |  | Planned | Actual | MH | Planned | Actual
[8 empty] | Effective |  |  |  | Effective | 0 | 0
[8 empty] | Foreman |  |  |  | Deviation
Main Delay Reasons
External Problems:
Internal Problems:
Action Plan to Process Improvement
Action Planning Date | Action |  | Date |  | Goal | Status | Responsible
|  |  | Planned | Actual/Projected
Main Solutions:
Produtivity Impact:
Responsible
[9 empty] | Buyer |  |  | Seller
[9 empty] | Responsible Name |  |  | Responsible Name
Navigation Panel