## Matriz
| CONTRACT No. XXXX.XXXXXXX.XX.X |  |  |  | Page 1 of 1
XXXX Field
Exhibit XIII - Risk Matrix
1. The objective of the Risk Matrix is to allocate risks and responsibilities between the PARTIES to enable the correct economic balance in the contract to be struck. The Risk Matrix shall be taken into account in any evaluation of financial losses by any of the PARTIES when supervening events arise that may affect the original contractual terms and conditions. Notwithstanding the foregoing, it is expressly established that the contents of this Exhibit XIII are for illustrative purposes only and are not meant to be an exhaustive and complete list of all the risks, obligations and liabilities of Seller pursuant to the Agreement.
2. Action plans to mitigate risks under contractual responsibility of Buyer are described only as a reference. Buyer shall not be obliged to perform any such plan and Buyer reserves the right to review and execute actions to mitigate risks according to the most up to date information and resources available during the project development.
RISK ID | RISKS (Causes and Consequences) | RISK IMPACT | ACTION PLAN | Contractual Responsibility
|  |  |  | BUYER | SELLER
1 | Contractual issues between Seller and its Subcontractors due to contractual disagreement between them. | Cost Increase, schedule delay | The mitigation plans shall be set out by Seller in its Risk Management Plan, as required in Exhibit VI – Planning&Control |  | X
2 | Schedule delays due to competition from other projects (high demand), including any other projects being carried out for Buyer | Schedule delay | The mitigation plans shall be set out by Seller in its Risk Management Plan, as required in Exhibit VI – Planning&Control |  | X
3 | Seller's engineering misinterpretation of Petrobras specification, design, contract and its exhibits, after conclusion of Basic Design (documents and Database) ENDORSEMENT process, as described in Exhibit III | Cost Increase, schedule delay | The mitigation plans shall be set out by Seller in its Risk Management Plan, as required in Exhibit VI – Planning&Control |  | X
4 | Materials and services quantities variation from Basic Design (documents and Database) ENDORSEMENT items, that were accepted by Buyer as impacting the Scope of Supply | Cost Increase | To be developed by Buyer | X
5 | Delay in the supply of materials and equipment under the responsibility of Seller. | Schedule delay | The mitigation plans shall be set out by Seller in its Risk Management Plan, as required in Exhibit VI – Planning&Control |  | X
6 | Delays due to temporary or permanent shortages of qualified manpower. | Schedule delay | The mitigation plans shall be set out by Seller in its Risk Management Plan, as required in Exhibit VI – Planning&Control |  | X
7 | Accidents during the execution of the contract including lifting operation, load in/outs, docking, lauching for equipments/modules/hull, modules temporary storage, Temporary mooring in sheltered waters and third part accident responsability. | Cost Increase, schedule delay | The mitigation plans shall be set out by Seller in its Risk Management Plan, as required in Exhibit VI – Planning&Control and Exhibit XII - Insurance Requirements |  | X
8 | Accidents during the transport of modules/hull to the integration shipyard or transport of the FPSO to Brazil up to the point of handover | Cost Increase, schedule delay | The mitigation plans shall be set out by Seller in its Risk Management Plan, as required in Exhibit VI – Planning&Control |  | X
9 | Accidents during the FPSO mooring hook up or risers pull in, at the final FPSO location, not caused by failures of the FPSO equipment or actions of Seller or its Subcontractors | Cost Increase, schedule delay | To be developed by Buyer | X
10 | Defective Works of product and services provided by Seller or its Subcontractors and vendors | Cost Increase, schedule delay | The mitigation plans shall be set out by Seller in its Risk Management Plan, as required in Exhibit VI – Planning&Control |  | X
11 | Delay on approval of FPSO by regulatory agencies (Navy, Aviation, National Petroleum, etc.) due to Seller non-compliance with requirements | Schedule delay | The mitigation plans shall be set out by Seller in its Risk Management Plan, as required in Exhibit VI – Planning&Control |  | X
12 | Delay on approval of enviromental licenses by Brazilian Enviromental Agency (IBAMA) due to non-compliance with environmental requirements not caused by Seller or its Subcobtractors | Schedule delay | To be developed by Buyer | X
13 | Partial or total paralisation of services due to climate conditions (other than Force Majeure conditions, as defined in the Agreement) | Schedule delay | The mitigation plans shall be set out by Seller in its Risk Management Plan, as required in Exhibit VI – Planning&Control |  | X
14 | Delay in the customs clearance process of FPSO by Brazilian authorities or authorities from any other countries, due to Seller non-compliance with requirements | Schedule delay | The mitigation plans shall be set out by Seller in its Risk Management Plan, as required in Exhibit VI – Planning&Control |  | X
15 | Partial or total paralisation of services by HSE authorities in Brazil or any other country due to Seller non-compliance with HSE regulations | Schedule delay | The mitigation plans shall be set out by Seller in its Risk Management Plan, as required in Exhibit VI – Planning&Control |  | X
16 | Partial or total paralisation of services by Labour Ministry authorities in Brazil or any other country due to Seller non-compliance with Labour regulations | Schedule delay | The mitigation plans shall be set out by Seller in its Risk Management Plan, as required in Exhibit VI – Planning&Control |  | X
17 | Cash Flow constraints or financial costs due to Seller delays on the achievement of payment milestones | Schedule delay | The mitigation plans shall be set out by Seller in its Risk Management Plan, as required in Exhibit VI – Planning&Control |  | X
18 | Partial or total paralisation of services due to strikes, except for strikes not related to Seller`s activities, notwithstanding Seller having taken reasonable actions to mitigate delays | Schedule delay | The mitigation plans shall be set out by Seller in its Risk Management Plan, as required in Exhibit VI – Planning&Control |  | X
19 | Extension of work or remobilization of third parties technical support teams, including vendors, for both onshore or offshore activities under Seller`s responsability | Cost Increase, schedule delay | The mitigation plans shall be set out by Seller in its Risk Management Plan, as required in Exhibit VI – Planning&Control |  | X
20 | Schedule disruptions or partial interruptions to the offshore comissioning activities due to safety issues (including work permit issuance process), urgent legal requirements and other disruptions not directly instructed by Buyer | Cost Increase, schedule delay | The mitigation plans shall be set out by Seller in its Risk Management Plan, as required in Exhibit VI – Planning&Control |  | X
21 | Variations in materials and services quantities due to the natural progression of the Detailing Engineering Design | Cost Increase | The mitigation plans shall be set out by Seller in its Risk Management Plan, as required in Exhibit VI – Planning&Control |  | X
22 | Variations in materials and services quantities from impacts and due to Change Orders previously authorized by Buyer to comply with changes in legislation ocurring after the Proposal Submission Date | Cost Increase | To be developed by Buyer | X
23 | Exchange rate and/or inflation variation | Cost Increase | The mitigation plans shall be set out by Seller in its Risk Management Plan, as required in Exhibit VI – Planning&Control |  | X