{"text_format":"1","workbook":"xlsx","n_sheets":26,"sheets":["Index","Data","C&A - Pipe - Spool","C&A - Pipe - Joint","C&A - Pipe - Support","C&A - Pipe - Valves","C&A - Structure","C&A - Structure - Joint","C&A - equipment","C&A - EIT","C&A - Coating","Procurement","Engineering","Planning - rundown_curves","Planning - Physical_S_Curves","Planning - Financial_S_Curves","Planning - resouce_histogram","Planning - executive_summary","Planning - programming","Planning - programming - item","Planning - milestones","Planning - risk","Planning - action_plan","Planning - KPI","Safety Studies","Standardized Color for 3D Model"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":1,"comments":27,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Index","index":0,"n_rows":52,"n_cols":2,"rows_kept":52,"cut":false,"hidden":false,"merged":[]}
[]
[]
[]
[null,"Navigation Panel"]
[]
[null,"Appendix 1 - C&A - Pipe - Spool"]
[]
[null,"Appendix 2 - C&A - Pipe - Joint"]
[]
[null,"Appendix 3 - C&A - Pipe - Support"]
[]
[null,"Appendix 4 - C&A - Pipe - Valves"]
[]
[null,"Appendix 5 - C&A - Structure"]
[]
[null,"Appendix 6 - C&A - Structure - Joint"]
[]
[null,"Appendix 7 - C&A - equipment"]
[]
[null,"Appendix 8 - C&A - EIT"]
[]
[null,"Appendix 9 - C&A - Coating"]
[]
[null,"Appendix 10 - Procurement"]
[]
[null,"Appendix 11 - Engineering"]
[]
[null,"Appendix 12 - Planning - rundown_curves"]
[]
[null,"Appendix 13 - Planning - Physical_S_Curves"]
[]
[null,"Appendix 14 - Planning - Financial_S_Curves"]
[]
[null,"Appendix 15 - Planning - resouce_histogram"]
[]
[null,"Appendix 16 - Planning - executive_summary"]
[]
[null,"Appendix 17 - Planning - programming"]
[]
[null,"Appendix 18 - Planning - programming - item"]
[]
[null,"Appendix 19 - Planning - milestones"]
[]
[null,"Appendix 20 - Planning - risk"]
[]
[null,"Appendix 21 - Planning - action_plan"]
[]
[null,"Appendix 22 - Planning - KPI"]
[]
[null,"Appendix 23 - Safety Studies"]
[]
[null,"Appendix 24 - Standardized Color for 3D Model"]

{"sheet":"Data","index":1,"n_rows":627,"n_cols":88,"rows_kept":627,"cut":false,"hidden":false,"merged":[]}
["Item","Specificity1","Specificity2","Specificity 3","attributes","attributes_revision","modify","data_type","attribute_description","attributes_type","fill_option_1","fill_option_2","fill_option_3","fill_option_4","fill_option_5","fill_option_6","fill_option_7","fill_option_8","fill_option_9","fill_option_10","fill_option_11","fill_option_12","fill_option_13","fill_option_14","fill_option_15","fill_option_16","fill_option_17","fill_option_18","fill_option_19","fill_option_20","fill_option_21","fill_option_22","fill_option_23","fill_option_24","fill_option_25","fill_option_26","fill_option_27","fill_option_28","fill_option_29","fill_option_30","fill_option_31","fill_option_32","fill_option_33","fill_option_34","fill_option_35","fill_option_36","fill_option_37","fill_option_38","fill_option_39","fill_option_40","fill_option_41","fill_option_42","fill_option_43","fill_option_44","fill_option_45","fill_option_46","fill_option_47","fill_option_48","fill_option_49","fill_option_50","fill_option_51","fill_option_52","fill_option_53","fill_option_54","fill_option_55","fill_option_56","fill_option_57","fill_option_58","fill_option_59","fill_option_60","fill_option_61","fill_option_62","fill_option_63","fill_option_64","fill_option_65","fill_option_66","fill_option_67","fill_option_68","fill_option_69","fill_option_70","fill_option_71","fill_option_72","fill_option_73","fill_option_74","fill_option_75","fill_option_76","fill_option_77","fill_option_78"]
[1,"C&A","Pipe","Spool","hull_or_topsides",0,"no_ change","Pull Down",null,"specific_attribute","hull","topsides"]
[2,"C&A","Pipe","Spool","block_or_module",1,"name_change","SYS Short Description Text 255","Block for hull or module for Topsides","specific_attribute"]
[3,"C&A","Pipe","Spool","site_fabrication",0,"no_ change","SYS Short Description Text 255","Where the spool will be fabricate","specific_attribute"]
[4,"C&A","Pipe","Spool","site_assembly",0,"no_ change","SYS Short Description Text 255","Where the spool will be assembly","specific_attribute"]
[5,"C&A","Pipe","Spool","sop",0,"no_ change","SYS Short Description Text 255","SOP code (if necessary)","specific_attribute"]
[6,"C&A","Pipe","Spool","ssop",0,"no_ change","SYS Short Description Text 255","SSOP code (if necessary)","specific_attribute"]
[7,"C&A","Pipe","Spool","sth",0,"no_ change","SYS Short Description Text 255","STH report number","specific_attribute"]
[8,"C&A","Pipe","Spool","isometric_number",0,"no_ change","SYS Short Description Text 255","isometric_number","specific_attribute"]
[9,"C&A","Pipe","Spool","Isometric_revision",0,"no_ change","SYS Short Description Text 255","Isometric_revision","specific_attribute"]
[10,"C&A","Pipe","Spool","P&ID_no",0,"no_ change","SYS Short Description Text 255","P&ID number","specific_attribute"]
[11,"C&A","Pipe","Spool","P&ID_revision",0,"no_ change","SYS Short Description Text 255","P&ID_revision","specific_attribute"]
[12,"C&A","Pipe","Spool","sheet_no",0,"no_ change","SYS Short Description Text 255","Spool shop/fabrication drawing  number.","specific_attribute"]
[13,"C&A","Pipe","Spool","elevation",0,"no_ change","SYS Short Description Text 255","The dimension of the elevation that the spool is physically assembled.","specific_attribute"]
[14,"C&A","Pipe","Spool","manufacture",0,"no_ change","SYS Short Description Text 255","Contractor / Site of manufacture.","specific_attribute"]
[15,"C&A","Pipe","Spool","pipe_Line",0,"no_ change","SYS Short Description Text 255","Pipe Line number (product - line number)","specific_attribute"]
[16,"C&A","Pipe","Spool","pipe_system",0,"no_ change","SYS Short Description Text 255","Pipe system number (System Description)","specific_attribute"]
[17,"C&A","Pipe","Spool","Spool",0,"no_ change","SYS Short Description Text 255","Spool number","primary_key"]
[18,"C&A","Pipe","Spool","piperun",0,"no_ change","SYS Short Description Text 255","Engineering pipeline attribute, with complete line code with line diameter. For exemple: 4\"-P-H10N-4213-PP.  Pipeline also exists but for example, it would be only the product and the line number: P-4213.","specific_attribute"]
[19,"C&A","Pipe","Spool","diameter_",0,"no_ change","Decimal Amount","Spool Diameter","specific_attribute"]
[20,"C&A","Pipe","Spool","thickness",0,"no_ change","Decimal Amount","Spool Thickness","specific_attribute"]
[21,"C&A","Pipe","Spool","weight",0,"no_ change","Decimal Amount","Spool Weight.","specific_attribute"]
[22,"C&A","Pipe","Spool","surface_area",0,"no_ change","Decimal Amount","Spool Surface_Area.","specific_attribute"]
[23,"C&A","Pipe","Spool","internal_coating",0,"no_ change","Pull Down",null,"specific_attribute","Yes","No"]
[24,"C&A","Pipe","Spool","internal_coating_type",0,"no_ change","SYS Short Description Text 255","Spool Internal_Coating_Type.","specific_attribute"]
[25,"C&A","Pipe","Spool","internal_coating_report",0,"no_ change","SYS Short Description Text 255","Spool Internal_Coating_Report Number","specific_attribute"]
[26,"C&A","Pipe","Spool","insulation",0,"no_ change","Pull Down",null,"specific_attribute","Yes","No"]
[27,"C&A","Pipe","Spool","insulation_type",0,"no_ change","Pull Down",null,"specific_attribute","NI (No isolation)","PP(Personal Protection)"]
[28,"C&A","Pipe","Spool","metal",0,"no_ change","Pull Down",null,"specific_attribute","AC","AL","AI","D","SD"]
[29,"C&A","Pipe","Spool","SPEC_BR",0,"no_ change","SYS Short Description Text 255","Pipe BR number (Br Description)","specific_attribute"]
[30,"C&A","Pipe","Spool","PN",0,"no_ change","SYS Short Description Text 255","Part Number according to the ASME","specific_attribute"]
[31,"C&A","Pipe","Spool","dimensional_report",0,"no_ change","SYS Short Description Text 255","Spool Dimensional_Report number","specific_attribute"]
[32,"C&A","Pipe","Spool","material_specification",0,"no_ change","SYS Short Description Text 255","Spool Material_Specification","specific_attribute"]
[33,"C&A","Pipe","Spool","chemical_cleaning",0,"no_ change","Pull Down",null,"specific_attribute","Yes","No"]
[34,"C&A","Pipe","Spool","coating_type",0,"no_ change","SYS Short Description Text 255","Spool Coating_Type","specific_attribute"]
[35,"C&A","Pipe","Spool","coating_report",0,"no_ change","SYS Short Description Text 255","Spool Coating_Report number","specific_attribute"]
[36,"C&A","Pipe","Spool","coating_touchup",0,"no_ change","SYS Short Description Text 255","Pipe touchup number (Touchup Description)","specific_attribute"]
[37,"C&A","Pipe","Spool","status_spool",0,"no_ change","Pull Down",null,"specific_attribute","00 - WS - Spool Canceled","01 - WS - Spool Hold","02 - WS - Waiting for material","03 - WS - Not Allocated","04 - WS - Not Started","05 - WS - Waiting Coupling","06 - WS - Waiting Material List Registration","07 - WS - Wainting for Alloy Identification","08 - WS - Wainting Welding","09 - WS - Waiting PT 1st Repair","10 - WS - Waiting PT 2nd Repair","11 - WS - Waiting Welding  1st Repair","12 - WS - Waiting Welding  2nd Repair","13 - WS - Waiting Visual","14 - WS - Waiting Visual  1st Repair","15 - WS - Waiting Visual -2nd Repair","16 - WS - Wainting  Approval Threaded/Glued Joint ","17 - WS - Wainting PT/MT","18 - WS - Wainting PT before PWHT","19 - WS - Wainting  RT/Paut","20 - WS - Wainting  hardness test","21 - WS - Wainting PWHT","22 - WS - Wainting hardness  after PWHT","23 - WS - Wainting PT after PWHT","24 - WS - Wainting RT/Paut after PWHT","25 - WS - Wainting tightness","26 - WS - Wainting ferrite test","27 - WS - Wainting traceability TAG","28 - WS - Wainting dimensional","29 - WS - Wainting Hydrostatic test","30 - WS - Wainting for painting condition definition","31 - WS - Wainting Metallization","32 - WS - Wainting Metallization/Coating","33 - WS - Wainting Coating/Painting","34 - WS - Wainting electroplating","35 - WS - Wainting iron-blast/Primer","36 - WS - Wainting Intermediate Painting","37 - WS - Wainting  Painting finishing","38 - Assembly not started","39 - C&A - Wainting Coupling","40 - C&A - Wainting Material List Registration","41 - C&A - Wainting Alloy Identification","42 - C&A - Wainting Welding","43 - C&A - Waiting PT 1st Repair","44 - C&A - Waiting PT 2nd Repair","45 - C&A - Wainting Welding 1st Repair","46 - C&A - Wainting Welding 2nd Repair","47 - C&A - Wainting Visual","48 - C&A - Wainting Visual 1st Repair","49 - C&A - Wainting Visual 2nd Repair","50 - C&A -   Approval Threaded/Glued Joint ","51 - C&A - Wainting PT/MT","52 - C&A - Wainting PT before PWHT","53 - C&A - Wainting RT/Paut","54 - C&A - Wainting hardness test","55 - C&A - Wainting PWHT","56 - C&A - Wainting hardness test after PWHT","57 - C&A - Wainting PT after PWHT","58 - C&A - Wainting RT/Paut after PWHT","59 - C&A - Wainting tighness","60 - C&A - Wainting thickness measurement","61 - C&A - Wainting support joint","62 - C&A - Wainting traceability","63 - C&A - Wainting field dimensional","64 - C&A - Wainting Metallization","65 - C&A - Waiting for Metalization/Coating","66 - C&A - Waiting for Coating/Painting","67 - C&A- Waiting for Galvanization","68 - C&A - Waiting for painting","69 - C&A - Waiting for Support","70 - C&A - Waiting for Hydrostatic test","71 - C&A - Waiting for Washing","73 - C&A - Waiting for Accessories","73 - C&A - Waiting for Painting touch","74 - C&A - Waiting Thermal Insulation","75 - C&A - Waiting for conditioning ","76 - C&A - Waiting for Documentation","77 - C&A - Spool Assembled and Released"]
[38,"C&A","Pipe","Joint","hull_or_topside",0,"no_ change","Pull Down",null,"specific_attribute","hull","topsides"]
[39,"C&A","Pipe","Joint","block_or_module",1,"name_change","SYS Short Description Text 255","Block for hull or module for Topsides","specific_attribute"]
[40,"C&A","Pipe","Joint","P&ID_no",0,"no_ change","SYS Short Description Text 255","P&ID number","specific_attribute"]
[41,"C&A","Pipe","Joint","P&ID_revision",0,"no_ change","SYS Short Description Text 255","P&ID_revision","specific_attribute"]
[42,"C&A","Pipe","Joint","sop",0,"no_ change","SYS Short Description Text 255","SOP code (if necessary)","specific_attribute"]
[43,"C&A","Pipe","Joint","ssop",0,"no_ change","SYS Short Description Text 255","SSOP code (if necessary)","specific_attribute"]
[44,"C&A","Pipe","Joint","sth",0,"no_ change","SYS Short Description Text 255","sth","specific_attribute"]
[45,"C&A","Pipe","Joint","Spool",0,"no_ change","SYS Short Description Text 255","Spool","foreign_key"]
[46,"C&A","Pipe","Joint","Joint",0,"no_ change","SYS Short Description Text 255","Joint number","primary_key"]
[47,"C&A","Pipe","Joint","diameter_",0,"no_ change","Decimal Amount","Joint Diameter.","specific_attribute"]
[48,"C&A","Pipe","Joint","FW_PW",0,"no_ change","Pull Down","Field Weld or Pipeshop Welding","specific_attribute","FW","PW"]
[49,"C&A","Pipe","Joint","weld_type",0,"no_ change","SYS Short Description Text 255","Joint Weld_Type.","specific_attribute"]
[50,"C&A","Pipe","Joint","inpection_class",0,"no_ change","SYS Short Description Text 255","Joint Inpection_Class.","specific_attribute"]
[51,"C&A","Pipe","Joint","weld_volume",0,"no_ change","SYS Short Description Text 255","Joint Weld_Volume.","specific_attribute"]
[52,"C&A","Pipe","Joint","fit_up",0,"no_ change","SYS Short Description Text 255","Fit_up report number.","specific_attribute"]
[53,"C&A","Pipe","Joint","1st_repair_report",0,"no_ change","SYS Short Description Text 255","Joint 1St_Repair_Report number","specific_attribute"]
[54,"C&A","Pipe","Joint","2st_repair_report",0,"no_ change","SYS Short Description Text 255","Joint 2St_Repair_Report number","specific_attribute"]
[55,"C&A","Pipe","Joint","visual",0,"no_ change","SYS Short Description Text 255","Joint Visual Report number","specific_attribute"]
[56,"C&A","Pipe","Joint","visual__1st_repair",0,"no_ change","SYS Short Description Text 255","Joint Visual _1St_Repair Report number","specific_attribute"]
[57,"C&A","Pipe","Joint","visual__2nd_repair",0,"no_ change","SYS Short Description Text 255","Joint Visual _2Nd_Repair Report number","specific_attribute"]
[58,"C&A","Pipe","Joint","MT_pt_before_welding",0,"no_ change","SYS Short Description Text 255","Magnetic particle testing/Penetrating Liquid Testing","specific_attribute"]
[59,"C&A","Pipe","Joint","MT_PT_bevel",0,"no_ change","SYS Short Description Text 255","Magnetic particle testing/Penetrating Liquid Testing","specific_attribute"]
[60,"C&A","Pipe","Joint","MT_PT_weld",0,"no_ change","SYS Short Description Text 255","Joint Penetrating Liquids and Magnetic Particles Report number","specific_attribute"]
[61,"C&A","Pipe","Joint","MT_PT_1st_Repair",0,"no_ change","SYS Short Description Text 255","Joint Mt_Pt_1St_Repair Report number","specific_attribute"]
[62,"C&A","Pipe","Joint","MT_PT_2nd_Repair",0,"no_ change","SYS Short Description Text 255","Joint Mt_Pt_2Nd_Repair Report number","specific_attribute"]
[63,"C&A","Pipe","Joint","RT_Paut",0,"no_ change","SYS Short Description Text 255","Raio X testing/Phase Array Ultrasonic Testing (PAUT)","specific_attribute"]
[64,"C&A","Pipe","Joint","RT_Paut_1st_Repair",0,"no_ change","SYS Short Description Text 255","Joint RX test / Phased Array test _1St_Repair Report number","specific_attribute"]
[65,"C&A","Pipe","Joint","RT_Paut_2st_Repair",0,"no_ change","SYS Short Description Text 255","Joint  RX test / Phased Array test_2St_Repair Report number","specific_attribute"]
[66,"C&A","Pipe","Joint","hardness_test",0,"no_ change","SYS Short Description Text 255","Joint hardness teste report number","specific_attribute"]
[67,"C&A","Pipe","Joint","PWHT",0,"no_ change","SYS Short Description Text 255","Post Weld Heat Treatment","specific_attribute"]
[68,"C&A","Pipe","Joint","PMI",0,"no_ change","SYS Short Description Text 255","Positive Material Identification","specific_attribute"]
[69,"C&A","Pipe","Joint","ferrite_test",0,"no_ change","SYS Short Description Text 255","Ferrite Test","specific_attribute"]
[70,"C&A","Pipe","Joint","remark",0,"no_ change","SYS Short Description Text 255","Pipe remark number (Remark Description)","specific_attribute"]
[71,"C&A","Pipe","Joint","WPS",0,"no_ change","SYS Short Description Text 255","Welding Procedure Specification","specific_attribute"]
[72,"C&A","Pipe","Joint","heat_1",0,"no_ change","SYS Short Description Text 255","Heat Number from the material of side 1","specific_attribute"]
[73,"C&A","Pipe","Joint","Lot_1",0,"no_ change","SYS Short Description Text 255","Pipe 1 number (product - 1 number)","specific_attribute"]
[74,"C&A","Pipe","Joint","Heat_2",0,"no_ change","SYS Short Description Text 255","Heat Number 2","specific_attribute"]
[75,"C&A","Pipe","Joint","Lot_2",0,"no_ change","SYS Short Description Text 255","Pipe 2 number (product - 2 number)","specific_attribute"]
[76,"C&A","Pipe","Joint","1st_Consumable",0,"no_ change","SYS Short Description Text 255","Consumable Certificate from the 1st welding Process","specific_attribute"]
[77,"C&A","Pipe","Joint","2nd_Consumable",0,"no_ change","SYS Short Description Text 255","Consumable Certificate from the 2nd welding Process","specific_attribute"]
[78,"C&A","Pipe","Joint","welder_number_root",0,"no_ change","SYS Short Description Text 255","Joint Welder_Number_Root Number","specific_attribute"]
[79,"C&A","Pipe","Joint","welder_number_root__1st_repair",0,"no_ change","SYS Short Description Text 255","Joint Welder_Number_Root_ 1St_Repair Number","specific_attribute"]
[80,"C&A","Pipe","Joint","welder_number_root__2st_repair",0,"no_ change","SYS Short Description Text 255","Joint Welder_Number_Root_ 2St_Repair Number","specific_attribute"]
[81,"C&A","Pipe","Joint","welder_number_buildup",0,"no_ change","SYS Short Description Text 255","Joint Welder_Number_Buildup Number","specific_attribute"]
[82,"C&A","Pipe","Joint","welder_number_buildup_1st_Repair",0,"no_ change","SYS Short Description Text 255","Pipe Repair number (product - repair number)","specific_attribute"]
[83,"C&A","Pipe","Joint","welder_number_buildup_2st_Repair",0,"no_ change","SYS Short Description Text 255","Pipe Repair number (product - repair number)","specific_attribute"]
[84,"C&A","Pipe","Joint","status_pipe_joint",0,"no_ change","Pull Down",null,"specific_attribute","00 - Joint not started","01 - Wainting coupling","02 - Wainting fitup visual","03 - Wainting Welding","04 - Wainting  Approval Threaded/Glued Joint  ","05- Waiting PT 1st Repair","06 - Waiting PT 2nd Repair","07 - Waiting Welding  1st Repair","08 - Waiting Welding  2nd Repair","09 - WS - Waiting Visual  1st Repair","10 - Waiting Visual -2nd Repair","11 - Wainting PT/MT","12 - Wainting PT before PWHT","13 - Wainting  RT/Paut","14 - Wainting  hardness test","15 - Wainting PWHT","16 - Wainting hardness  after PWHT","17 - Wainting PT after PWHT","18 - Wainting RT/Paut after PWHT","19 - Approved Weld"]
[85,"C&A","Pipe","Support","hull_or_topside",0,"no_ change","Pull Down",null,"specific_attribute","hull ","topsides"]
[86,"C&A","Pipe","Support","block_or_module",1,"name_change","SYS Short Description Text 255","Pipe module number (Module Description)","specific_attribute"]
[87,"C&A","Pipe","Support","site_fabrication",0,"no_ change","SYS Short Description Text 255","Pipe fabrication Site.","specific_attribute"]
[88,"C&A","Pipe","Support","site_assembly",0,"no_ change","SYS Short Description Text 255","Pipe assembly Site.","specific_attribute"]
[89,"C&A","Pipe","Support","support_tag",0,"no_ change","SYS Short Description Text 255","Pipe tag number","primary_key"]
[90,"C&A","Pipe","Support","pipe_line",0,"no_ change","SYS Short Description Text 255","Pipe line number","specific_attribute"]
[91,"C&A","Pipe","Support","spool",0,"no_ change","SYS Short Description Text 255","Pipe spool number","foreign_key"]
[92,"C&A","Pipe","Support","isometric_number",0,"no_ change","SYS Short Description Text 255","Pipe number number","specific_attribute"]
[93,"C&A","Pipe","Support","Isometric_revision",0,"no_ change","SYS Short Description Text 255","Pipe isometric revision number","specific_attribute"]
[94,"C&A","Pipe","Support","support_type",0,"no_ change","SYS Short Description Text 255","Typical support code.","specific_attribute"]
[95,"C&A","Pipe","Support","manufacture",0,"no_ change","SYS Short Description Text 255","Pipe manufacture site","specific_attribute"]
[96,"C&A","Pipe","Support","weight",0,"no_ change","Decimal Amount","weight","specific_attribute"]
[97,"C&A","Pipe","Support","status_pipe_support",0,"no_ change","Pull Down",null,"specific_attribute","00 - Not Started","01 - Wainting Manufacture","02 - Waiting Painting","03 - Assembly not started","04 - Waiting Welding","05 - Waiting Field Painting","06 - Assembled Support"]
[98,"C&A","Pipe","Valves","valve",0,"no_ change","SYS Short Description Text 255","valve tag","primary_key"]
[99,"C&A","Pipe","Valves","drawing_no",0,"no_ change","SYS Short Description Text 255","drawing_no","specific_attribute"]
[100,"C&A","Pipe","Valves","P&ID_no",0,"no_ change","SYS Short Description Text 255","P&ID number","specific_attribute"]
[101,"C&A","Pipe","Valves","P&ID_revision",0,"no_ change","SYS Short Description Text 255","P&ID_revision","specific_attribute"]
[102,"C&A","Pipe","Valves","pipe_line",0,"no_ change","SYS Short Description Text 255","valve pipe_line number","specific_attribute"]
[103,"C&A","Pipe","Valves","isometric_number",0,"no_ change","SYS Short Description Text 255","isometric_number","specific_attribute"]
[104,"C&A","Pipe","Valves","Isometric_revision",0,"no_ change","SYS Short Description Text 255","Isometric_revision","specific_attribute"]
[105,"C&A","Pipe","Valves","manufacture",0,"no_ change","SYS Short Description Text 255","Valve Vendor / Supplyer","specific_attribute"]
[106,"C&A","Pipe","Valves","model_manufacture",0,"no_ change","SYS Short Description Text 255","Valve vendor / Supplyer Model / type","specific_attribute"]
[107,"C&A","Pipe","Valves","diamenter",0,"no_ change","SYS Short Description Text 255","Valve Diameter.","specific_attribute"]
[108,"C&A","Pipe","Valves","status_pipe_valves",0,"no_ change","Pull Down",null,"specific_attribute","00 - Not received","01 - Assembly not started","02 - Assembled Valve"]
[109,"C&A","Structure","null","hull_or_topside",0,"no_ change","SYS Short Description Text 255","hull_or_topside","specific_attribute"]
[110,"C&A","Structure","null","block_or_module",1,"name_change","SYS Short Description Text 255","Block for hull or module for Topsides","specific_attribute"]
[111,"C&A","Structure","null","structure_type",0,"no_ change","SYS Short Description Text 255","Primary, secondary or terciary structure.","specific_attribute"]
[112,"C&A","Structure","null","structure_element",0,"no_ change","SYS Short Description Text 255","This is the primary key of the worksheet, it is a code that identifies the structural element to be possible to join in the 3D model.","primary_key"]
[113,"C&A","Structure","null","structure_type",0,"no_ change","Pull Down","Is repeated. Can be cancelled.","specific_attribute","Primary","Secondary","Tertiary"]
[114,"C&A","Structure","null","drawing_br",0,"no_ change","SYS Short Description Text 255","Petrobras Drawing Reference","specific_attribute"]
[115,"C&A","Structure","null","drawing_revision",0,"no_ change","SYS Short Description Text 255","drawing_revision","specific_attribute"]
[116,"C&A","Structure","null","assembly_drawing",0,"no_ change","SYS Short Description Text 255","We already have an attribute for shop drawing with the name manufacture_drawing. Assembly_drawing are the assembly drawings that the contractor usually issues to field personnel.","specific_attribute"]
[117,"C&A","Structure","null","assembly_drawing_revision",0,"no_ change","SYS Short Description Text 255","Structure assembly drawing revision","specific_attribute"]
[118,"C&A","Structure","null","manufacture_drawing",0,"no_ change","SYS Short Description Text 255","Manufacture Drawing Number","specific_attribute"]
[119,"C&A","Structure","null","manufacture_drawing_revision",0,"no_ change","SYS Short Description Text 255","Structure manufacture drawing revision","specific_attribute"]
[120,"C&A","Structure","null","material_specification",0,"no_ change","SYS Short Description Text 255","Material description","specific_attribute"]
[121,"C&A","Structure","null","weight",0,"no_ change","Decimal Amount","weight","specific_attribute"]
[122,"C&A","Structure","null","coating_type",0,"no_ change","SYS Short Description Text 255","coating_type","specific_attribute"]
[123,"C&A","Structure","null","coating_report",0,"no_ change","SYS Short Description Text 255","coating_report","specific_attribute"]
[124,"C&A","Structure","null","coating_touchup",0,"no_ change","SYS Short Description Text 255","coating_touchup","specific_attribute"]
[125,"C&A","Structure","null","status_structure",0,"no_ change","Pull Down",null,"specific_attribute","00 - Not Started","01 - Wainting Manufacture","02 - Waiting Painting","03 - Assembly not started","04 - Waiting Welding","05 - Waiting Inspection","06 - Assembled Structure"]
[126,"C&A","Structure","Joint","hull_or_topside",0,"no_ change","SYS Short Description Text 255","hull_or_topside","specific_attribute"]
[127,"C&A","Structure","Joint","block_or_module",1,"name_change","SYS Short Description Text 255","Block for hull or module for Topsides","specific_attribute"]
[128,"C&A","Structure","Joint","structure_element",0,"no_ change","SYS Short Description Text 255","Structure element tag","foreign_key"]
[129,"C&A","Structure","Joint","joint",0,"no_ change","SYS Short Description Text 255","Structure Joint tag","primary_key"]
[130,"C&A","Structure","Joint","WW_FW",0,"no_ change","SYS Short Description Text 255","Workshop Weld / Field Weld","specific_attribute"]
[131,"C&A","Structure","Joint","weld_type",0,"no_ change","SYS Short Description Text 255","Joint Weld_Type (root/buildup)","specific_attribute"]
[132,"C&A","Structure","Joint","weld_extension",0,"no_ change","SYS Short Description Text 255","Weld extension in mm.","specific_attribute"]
[133,"C&A","Structure","Joint","group",0,"no_ change","SYS Short Description Text 255","Structure group","specific_attribute"]
[134,"C&A","Structure","Joint","inspection_level",0,"no_ change","SYS Short Description Text 255","inspection_level","specific_attribute"]
[135,"C&A","Structure","Joint","WPS",0,"no_ change","SYS Short Description Text 255","Welding Procedure Specification","specific_attribute"]
[136,"C&A","Structure","Joint","fit_up",0,"no_ change","SYS Short Description Text 255","Joint fit_up report number","specific_attribute"]
[137,"C&A","Structure","Joint","visual",0,"no_ change","SYS Short Description Text 255","Joint Visual report number","specific_attribute"]
[138,"C&A","Structure","Joint","PT",0,"no_ change","SYS Short Description Text 255","Penetrating Liquid Testing Report Number","specific_attribute"]
[139,"C&A","Structure","Joint","MT",0,"no_ change","SYS Short Description Text 255","Magnetic particle testing Report Number","specific_attribute"]
[140,"C&A","Structure","Joint","RX_US",0,"no_ change","SYS Short Description Text 255","Raio X testing/Ultrasonic Testing Report Number","specific_attribute"]
[141,"C&A","Structure","Joint","final_dimensional",0,"no_ change","SYS Short Description Text 255","Final Dimensional Assembly Report Number","specific_attribute"]
[142,"C&A","Structure","Joint","welder_number_root",0,"no_ change","SYS Short Description Text 255","welder_number_root","specific_attribute"]
[143,"C&A","Structure","Joint","welder_number_buildup",0,"no_ change","SYS Short Description Text 255","welder_number_buildup","specific_attribute"]
[144,"C&A","Structure","Joint","consumable",0,"no_ change","SYS Short Description Text 255","Structure Consumable report number","specific_attribute"]
[145,"C&A","Structure","Joint","status_structure_joint",0,"no_ change","SYS Short Description Text 255","Joint last step concluded","specific_attribute"]
[146,"C&A","equipment","null","hull_or_topside",0,"no_ change","SYS Short Description Text 255","hull_or_topside","specific_attribute"]
[147,"C&A","equipment","null","block_or_module",1,"name_change","SYS Short Description Text 255","Block for hull or module for Topsides","specific_attribute"]
[148,"C&A","equipment","null","sop",0,"no_ change","SYS Short Description Text 255","SOP code (if necessary)","specific_attribute"]
[149,"C&A","equipment","null","ssop",0,"no_ change","SYS Short Description Text 255","SSOP code (if necessary)","specific_attribute"]
[150,"C&A","equipment","null","equipment_tag",0,"no_ change","SYS Short Description Text 255","equipment_tag","primary_key"]
[151,"C&A","equipment","null","function_test",0,"no_ change","SYS Short Description Text 255","Function Test Report Number","specific_attribute"]
[152,"C&A","equipment","null","manufacturer",0,"no_ change","SYS Short Description Text 255","Equip. Vendor / Supplyer","specific_attribute"]
[153,"C&A","equipment","null","model_manufacturer",0,"no_ change","SYS Short Description Text 255","Equip. Vendor / Supplyer model / type","specific_attribute"]
[154,"C&A","equipment","null","Elevation_or_compartment",1,"name_change","SYS Short Description Text 255","Elevation","specific_attribute"]
[155,"C&A","equipment","null","Equipament_Tag",0,"no_ change","SYS Short Description Text 255","Repeated - cancel","specific_attribute"]
[156,"C&A","equipment","null","Description_Tag",0,"no_ change","SYS Short Description Text 255","Description Tag","specific_attribute"]
[157,"C&A","equipment","null","Drawing_No.",0,"no_ change","SYS Short Description Text 255","Drawing No. Equipment General Arrangement Drawing - w/ foot prints","specific_attribute"]
[158,"C&A","equipment","null","drawing_Revision",0,"no_ change","SYS Short Description Text 255","drawing_Revision","specific_attribute"]
[159,"C&A","equipment","null","status_equipment",0,"no_ change","Pull Down",null,"specific_attribute","00 - Not received","01 - Assembly not started","02 - Waiting Inspection","03 - Assembled Equipment"]
[160,"C&A","EIT","null","hull_or_topside",0,"no_ change","SYS Short Description Text 255","hull_or_topside","specific_attribute"]
[161,"C&A","EIT","null","block_or_module",1,"name_change","SYS Short Description Text 255","Block for hull or module for Topsides","specific_attribute"]
[162,"C&A","EIT","null","sop",0,"no_ change","SYS Short Description Text 255","SOP code (if necessary)","specific_attribute"]
[163,"C&A","EIT","null","ssop",0,"no_ change","SYS Short Description Text 255","SSOP code (if necessary)","specific_attribute"]
[164,"C&A","EIT","null","eit_tag",0,"no_ change","SYS Short Description Text 255","eit_tag","primary_key"]
[165,"C&A","EIT","null","item_type",0,"no_ change","Pull Down",null,"specific_attribute","Cable","Junction Box","Equipament","MCT","Cable Trays","Painel","Support","Suporte a quente","Reflector","Light Fixture","Electrical grounding","Tubing","Instrument"]
[166,"C&A","EIT","null","quantity",0,"no_ change","Decimal Amount","quantity","specific_attribute"]
[167,"C&A","EIT","null","quantity_unit",0,"no_ change","SYS Short Description Text 255","quantity unit","specific_attribute"]
[168,"C&A","EIT","null","pullin_cable_report",0,"no_ change","SYS Short Description Text 255","pullin_cable_report number","specific_attribute"]
[169,"C&A","EIT","null","conection_report",0,"no_ change","SYS Short Description Text 255","conection_report number","specific_attribute"]
[170,"C&A","EIT","null","assembly_report",0,"no_ change","SYS Short Description Text 255","assembly_report number","specific_attribute"]
[171,"C&A","EIT","null","hydrostec_test",0,"no_ change","SYS Short Description Text 255","Apply to tubbing / Report Number","specific_attribute"]
[172,"C&A","EIT","null","calibration_report",0,"no_ change","SYS Short Description Text 255","calibration_report number","specific_attribute"]
[173,"C&A","EIT","null","continuity_test",0,"no_ change","SYS Short Description Text 255","continuity_test report number","specific_attribute"]
[174,"C&A","EIT","null","megger_test",0,"no_ change","SYS Short Description Text 255","megger_test report number","specific_attribute"]
[175,"C&A","EIT","null","HIPOT_test",0,"no_ change","SYS Short Description Text 255","HIPOT_test report number","specific_attribute"]
[176,"C&A","EIT","null","status_eit",0,"no_ change","Pull Down",null,"specific_attribute","00 - Not received","01 - Assembly not started","02 - Waiting Inspection","05 - Assembled Item"]
[177,"C&A","Coating","null","hull_or_topsides",0,"no_ change","Pull Down",null,"specific_attribute","hull","topsides"]
[178,"C&A","Coating","null","Mega_block",0,"no_ change","SYS Short Description Text 255","If it is a hull, inform the mega block","specific_attribute"]
[179,"C&A","Coating","null","block_or_module",1,"name_change","SYS Short Description Text 255","Block for hull or module for Topsides","specific_attribute"]
[180,"C&A","Coating","null","discipline",0,"no_ change","Pull Down",null,"specific_attribute","Piping","Structure"]
[181,"C&A","Coating","null","item_type",0,"no_ change","Pull Down",null,"specific_attribute","outfitting","primary","secondary","tertiary","spool","support"]
[182,"C&A","Coating","null","item",0,"no_ change","SYS Short Description Text 255","Identification of component that will be paiting, hull block assembly erections joints","foreign_key"]
[183,"C&A","Coating","null","painting_system_code_petrobras",0,"no_ change","SYS Short Description Text 255","Painting System PETROBRAS","specific_attribute"]
[184,"C&A","Coating","null","painting_system_code_contractor",0,"no_ change","SYS Short Description Text 255","Painting System CONTRACTOR","specific_attribute"]
[185,"C&A","Coating","null","primary_surface_preparation_report",0,"no_ change","SYS Short Description Text 255","Report Number of Abrasive Blast Primary","specific_attribute"]
[186,"C&A","Coating","null","secondary_surface_preparation_report",0,"no_ change","SYS Short Description Text 255","Report Number of Abrasive Blast Secondary","specific_attribute"]
[187,"C&A","Coating","null","painting_report",0,"no_ change","SYS Short Description Text 255","Number of Paiting Inspection Report","specific_attribute"]
[188,"C&A","Coating","null","touchup_report",0,"no_ change","SYS Short Description Text 255","Number of Touchup Report","specific_attribute"]
[189,"C&A","Coating","null","field_painting_report",0,"no_ change","SYS Short Description Text 255","Number of Field Inspection Report","specific_attribute"]
[190,"C&A","Coating","null","surface_preparation_holdpoint_inspection",0,"no_ change","Pull Down",null,"specific_attribute","yes","no"]
[191,"C&A","Coating","null","1st_coating_holdpoint_inspection",0,"no_ change","Pull Down",null,"specific_attribute","yes","no"]
[192,"C&A","Coating","null","2nd_coating_holdpoint_inspection",0,"no_ change","Pull Down",null,"specific_attribute","yes","no"]
[193,"C&A","Coating","null","3rd_coating_holdpoint_inspection",0,"no_ change","Pull Down",null,"specific_attribute","yes","no"]
[194,"C&A","Coating","null","4th_coating_holdpoint_inspection",0,"no_ change","Pull Down",null,"specific_attribute","yes","no"]
[195,"C&A","Coating","null","date_surface_preparation_holdpoint_inspection",0,"no_ change","Date Only Picker","Date Plan for Owner Surface  Preparation Inspection","specific_attribute"]
[196,"C&A","Coating","null","date_1st_coating_holdpoint_inspection",0,"no_ change","Date Only Picker","Date Plan for Owner 1st Coating Inspection","specific_attribute"]
[197,"C&A","Coating","null","date_2nd_coating_holdpoint_inspection",0,"no_ change","Date Only Picker","Date Plan for Owner 2nd Coating Inspection","specific_attribute"]
[198,"C&A","Coating","null","date_3rd_coating_holdpoint_inspection",0,"no_ change","Date Only Picker","Date Plan for Owner 3rd Coating Inspection","specific_attribute"]
[199,"C&A","Coating","null","date_4th_coating_holdpoint_inspection",0,"no_ change","Date Only Picker","Date Plan for Owner 4th Coating Inspection","specific_attribute"]
[200,"C&A","Coating","null","problems_history",0,"no_ change","SYS Short Description Text 255","problems_history description","specific_attribute"]
[201,"C&A","Coating","null","status_coating",0,"no_ change","Pull Down",null,"specific_attribute","00 - Waiting Surface Preparation","01 - Waiting First Coating","02 - Waiting Second Coating","03 - Waiting Third Coating","04 - Waiting Fourth Coating","05 - Wainting Surface Preparation Field","06 - Waiting Field Painting","07 - Wainting Inspection Field","08 - Coating Approved"]
[202,"Procurement","null","null","hull_or_topside",1,"delete",null,null,"specific_attribute","hull ","topsides"]
[203,"Procurement","null","null","module",1,"delete",null,"module","specific_attribute"]
[204,"Procurement","null","null","Request_Document",1,"delete",null,"Request_Document Number","specific_attribute"]
[205,"Procurement","null","null","request_document_revision",1,"delete",null,"request_document_revision","specific_attribute"]
[206,"Procurement","null","null","item_tag",0,"no_ change","SYS Short Description Text 255","item_tag","primary_key"]
[207,"Procurement","null","null","SOP",1,"delete",null,"SOP code (if necessary)","specific_attribute"]
[208,"Procurement","null","null","SSOP",1,"delete",null,"SSOP code (if necessary)","specific_attribute"]
[209,"Procurement","null","null","PO",1,"delete",null,"PO code (if necessary)","specific_attribute"]
[210,"Procurement","null","null","PO_revision",1,"delete",null,"PO_revision","specific_attribute"]
[211,"Procurement","null","null","PO_item",1,"delete",null,"PO_item","specific_attribute"]
[212,"Procurement","null","null","discipline",1,"delete",null,null,"specific_attribute","Mechanics","Piping","Eletric","Instrumentation","Telecom","Security","Structure"]
[213,"Procurement","null","null","manufacture",1,"delete",null,"manufacture","specific_attribute"]
[214,"Procurement","null","null","model_manufacturer",1,"delete",null,"model_manufacturer","specific_attribute"]
[215,"Procurement","null","null","type",1,"delete",null,null,"specific_attribute","Bulk Material","Tagged Item"]
[216,"Procurement","null","null","item_description",1,"delete",null,"item_description","specific_attribute"]
[217,"Procurement","null","null","BR_code",1,"delete",null,"Code PETROBRAS","specific_attribute"]
[218,"Procurement","null","null","Contractor_Code",1,"delete",null,"Contractor_Code Number","specific_attribute"]
[219,"Procurement","null","null","SPEC",1,"delete",null,"SPEC code (if necessary)","specific_attribute"]
[220,"Procurement","null","null","Dim_#1",1,"delete",null,"Dimmension #1","specific_attribute"]
[221,"Procurement","null","null","Dim_#2",1,"delete",null,"Dimmension #2","specific_attribute"]
[222,"Procurement","null","null","Dim_#3",1,"delete",null,"Dimmension #3","specific_attribute"]
[223,"Procurement","null","null","quantity",1,"delete",null,"quantity","specific_attribute"]
[224,"Procurement","null","null","quantity_unit.",1,"delete",null,null,"specific_attribute","m ","m²","Un."]
[225,"Procurement","null","null","balance_to_Buy",1,"delete",null,"balance_to_Buy quantity","specific_attribute"]
[226,"Procurement","null","null","dispatcher",1,"delete",null,"dispatcher","specific_attribute"]
[227,"Procurement","null","null","origin",1,"delete",null,"origin","specific_attribute"]
[228,"Procurement","null","null","inspection_type",1,"delete",null,null,"specific_attribute","A","B","C"]
[229,"Procurement","null","null","Inspetor_residente",1,"delete",null,"Inspector name / code","specific_attribute"]
[230,"Procurement","null","null","PIM_foreseen",1,"delete",null,"PIM_foreseen date","specific_attribute"]
[231,"Procurement","null","null","PIM_confirmed",1,"delete",null,"PIM_confirmed date","specific_attribute"]
[232,"Procurement","null","null","PIM_actual_date",1,"delete",null,"PIM_actor name / code","specific_attribute"]
[233,"Procurement","null","null","IMETRO_certificate",1,"delete",null,null,"specific_attribute","yes","no"]
[234,"Procurement","null","null","IMETRO_foreseen",1,"delete",null,"INMETRO_foreseen date","specific_attribute"]
[235,"Procurement","null","null","IMETRO_actual_date",1,"delete",null,"IMETRO_actual_date","specific_attribute"]
[236,"Procurement","null","null","DNV_Classification",1,"delete",null,null,"specific_attribute","NV","W","NA"]
[237,"Procurement","null","null","delivery_conditions",1,"delete",null,null,"specific_attribute","CIF","FOT","FOB","EXW","CIP"]
[238,"Procurement","null","null","change_order_No",1,"delete",null,"If the item refers to a change order, indicate the number","specific_attribute"]
[239,"Procurement","null","null","procurement_status",1,"delete",null,null,"specific_attribute","00 - RM not issued","01 - RM issued","02 - RM in cotation","03 - Proposal in Technical Analysis","04 - PO issued","05 - Manufacturing in progress","06 - Partially delivered","07 - Total Delivery","08 - RM Canceled","09 - RM Hold"]
[240,"Engineering","null","null","SOP",0,"no_ change","SYS Short Description Text 255","SOP code (if necessary)","specific_attribute"]
[241,"Engineering","null","null","SSOP",0,"no_ change","SYS Short Description Text 255","SSOP code (if necessary)","specific_attribute"]
[242,"Engineering","null","null","hull_or_topsides",0,"no_ change","Pull Down",null,"specific_attribute","hull","topsides"]
[243,"Engineering","null","null","Vendor_name",0,"no_ change","SYS Short Description Text 255","Vendor_name","specific_attribute"]
[244,"Engineering","null","null","dicipline_owner",0,"no_ change","SYS Short Description Text 255","Inform document discipline by Owner","specific_attribute"]
[245,"Engineering","null","null","discipline_contractor",0,"no_ change","SYS Short Description Text 255","Inform document discipline by Seller/Contractor.","specific_attribute"]
[246,"Engineering","null","null","operation_MWS",0,"no_ change","SYS Short Description Text 255","MWS review required (yes/no)","specific_attribute"]
[247,"Engineering","null","null","document_type",0,"no_ change","SYS Short Description Text 255","document_type","specific_attribute"]
[248,"Engineering","null","null","document_number",0,"no_ change","SYS Short Description Text 255","document_number","primary_key"]
[249,"Engineering","null","null","document_title",0,"no_ change","SYS Short Description Text 255","document_title","specific_attribute"]
[250,"Engineering","null","null","reason_revision",0,"no_ change","SYS Short Description Text 255","Example: Detailment, for construction, as built...","specific_attribute"]
[251,"Engineering","null","null","last_issued_revision",0,"no_ change","SYS Short Description Text 255","last_issued_revision","specific_attribute"]
[252,"Engineering","null","null","last__issued_date",0,"no_ change","Date Only Picker","last__issued_date","specific_attribute"]
[253,"Engineering","null","null","asbuilt_status",0,"no_ change","SYS Short Description Text 255","asbuilt_status","specific_attribute"]
[254,"Engineering","null","null","3D_model_status",0,"no_ change","SYS Short Description Text 255","Inform if 3d model is updated with last document revision.","specific_attribute"]
[255,"Engineering","null","null","owner_status",0,"no_ change","SYS Short Description Text 255","owner_status","specific_attribute"]
[256,"Engineering","null","null","classfication_society_status",0,"no_ change","SYS Short Description Text 255","classfication_society_status","specific_attribute"]
[257,"Engineering","null","null","MWS_status",0,"no_ change","SYS Short Description Text 255","MWS_status","specific_attribute"]
[258,"Engineering","null","null","Final_status",0,"no_ change","SYS Short Description Text 255","Inform actual document status. For exemple: For comments, reproved, issued...","specific_attribute"]
[259,"Engineering","null","null","0_issue_planned_date",0,"no_ change","Date Only Picker","Planned issue date of revision 0","specific_attribute"]
[260,"Engineering","null","null","A_issue_planned_date",0,"no_ change","Date Only Picker","Planned issue date of revision A","specific_attribute"]
[261,"Engineering","null","null","B_issue_planned_date",0,"no_ change","Date Only Picker","Planned issue date of revision B","specific_attribute"]
[262,"Engineering","null","null","C_issue_planned_date",0,"no_ change","Date Only Picker","Planned issue date of revision C","specific_attribute"]
[263,"Engineering","null","null","D_issue_planned_date",0,"no_ change","Date Only Picker","Planned issue date of revision D","specific_attribute"]
[264,"Engineering","null","null","E_issue_planned_date",0,"no_ change","Date Only Picker","Planned issue date of revision E. Forecast E revision date.","specific_attribute"]
[265,"Engineering","null","null","0_issued_date",0,"no_ change","Date Only Picker","Date revision 0 was issued","specific_attribute"]
[266,"Engineering","null","null","A_issued_date",0,"no_ change","Date Only Picker","Date revision A was issued","specific_attribute"]
[267,"Engineering","null","null","B_issued_date",0,"no_ change","Date Only Picker","Date revision B was issued","specific_attribute"]
[268,"Engineering","null","null","C_issued_date",0,"no_ change","Date Only Picker","Date revision C was issued","specific_attribute"]
[269,"Engineering","null","null","D_issued_date",0,"no_ change","Date Only Picker","Date revision D was issued","specific_attribute"]
[270,"Engineering","null","null","E_issued_date",0,"no_ change","Date Only Picker","Date revision E was issued","specific_attribute"]
[271,"Engineering","null","null","0_submit_owner_date",0,"no_ change","Date Only Picker","Submission date for review 0 to PETROBRAS","specific_attribute"]
[272,"Engineering","null","null","0_received_owner_comments_date",0,"no_ change","Date Only Picker","Receipt date of review 0 comments made by PETROBRAS","specific_attribute"]
[273,"Engineering","null","null","A_submit_owner_date",0,"no_ change","Date Only Picker","Submission date for review A to PETROBRAS","specific_attribute"]
[274,"Engineering","null","null","A_received_owner_comments_date",0,"no_ change","Date Only Picker","Receipt date of review A comments made by PETROBRAS","specific_attribute"]
[275,"Engineering","null","null","B_submit_owner_date",0,"no_ change","Date Only Picker","Submission date for review B to PETROBRAS","specific_attribute"]
[276,"Engineering","null","null","B_receive_owner_comments_date",0,"no_ change","Date Only Picker","Receipt date of review B comments made by PETROBRAS","specific_attribute"]
[277,"Engineering","null","null","C_submit_owner_date",0,"no_ change","Date Only Picker","Submission date for review C to PETROBRAS","specific_attribute"]
[278,"Engineering","null","null","C_received_owner_comments_date",0,"no_ change","Date Only Picker","Receipt date of review C comments made by PETROBRAS","specific_attribute"]
[279,"Engineering","null","null","D_submit_owner_date",0,"no_ change","Date Only Picker","Submission date for review D to PETROBRAS","specific_attribute"]
[280,"Engineering","null","null","D_received_owner_comments_date",0,"no_ change","Date Only Picker","Receipt date of review D comments made by PETROBRAS","specific_attribute"]
[281,"Engineering","null","null","E_submit_owner_date",0,"no_ change","Date Only Picker","Submission date for review E to PETROBRAS","specific_attribute"]
[282,"Engineering","null","null","E_received_owner_comments_date",0,"no_ change","Date Only Picker","Receipt date of review E comments made by PETROBRAS","specific_attribute"]
[283,"Engineering","null","null","0_submit_CS_date",0,"no_ change","Date Only Picker","Submission date for review 0 to Classification Society","specific_attribute"]
[284,"Engineering","null","null","0_received_CS_comments_date",0,"no_ change","Date Only Picker","Receipt date of review 0 comments made by Classification society","specific_attribute"]
[285,"Engineering","null","null","A_submit_CS_date",0,"no_ change","Date Only Picker","Submission date for review A to Classification Society","specific_attribute"]
[286,"Engineering","null","null","A_received_CS_comments_date",0,"no_ change","Date Only Picker","Receipt date of review A comments made by Classification society","specific_attribute"]
[287,"Engineering","null","null","B_submit_CS_date",0,"no_ change","Date Only Picker","Submission date for review B to Classification Society","specific_attribute"]
[288,"Engineering","null","null","B_received_CS_comments_Date",0,"no_ change","Date Only Picker","Receipt date of review B comments made by Classification society","specific_attribute"]
[289,"Engineering","null","null","C_submit_CS_date",0,"no_ change","Date Only Picker","Submission date for review C to Classification Society","specific_attribute"]
[290,"Engineering","null","null","C_received_CS_comments_date",0,"no_ change","Date Only Picker","Receipt date of review C comments made by Classification society","specific_attribute"]
[291,"Engineering","null","null","D_submit_CS_date",0,"no_ change","Date Only Picker","Submission date for review D to Classification Society","specific_attribute"]
[292,"Engineering","null","null","D_received_CS_comments_Date",0,"no_ change","Date Only Picker","Receipt date of review D comments made by Classification society","specific_attribute"]
[293,"Engineering","null","null","E_submit_CS_date",0,"no_ change","Date Only Picker","Submission date for review E to Classification Society","specific_attribute"]
[294,"Engineering","null","null","E_received_CS_comments_date",0,"no_ change","Date Only Picker","Receipt date of review E comments made by Classification society","specific_attribute"]
[295,"Engineering","null","null","0_submit_MWS_date",0,"no_ change","Date Only Picker","Submission date for review 0 to Marine Warranty Surveyor","specific_attribute"]
[296,"Engineering","null","null","0_received_MWS_comments_date",0,"no_ change","Date Only Picker","Receipt date of review 0 comments made by Marine Warranty Surveyor","specific_attribute"]
[297,"Engineering","null","null","A_submit_MWS_date",0,"no_ change","Date Only Picker","Submission date for review A to Marine Warranty Surveyor","specific_attribute"]
[298,"Engineering","null","null","A_received_MWS_comments_date",0,"no_ change","Date Only Picker","Receipt date of review A comments made by Marine Warranty Surveyor","specific_attribute"]
[299,"Engineering","null","null","B_submit_MWS_date",0,"no_ change","Date Only Picker","Submission date for review B to Marine Warranty Surveyor","specific_attribute"]
[300,"Engineering","null","null","B_received_MWS_comments_Date",0,"no_ change","Date Only Picker","Receipt date of review B comments made by Marine Warranty Surveyor","specific_attribute"]
[301,"Engineering","null","null","C_submit_MWS_date",0,"no_ change","Date Only Picker","Submission date for review C to Marine Warranty Surveyor","specific_attribute"]
[302,"Engineering","null","null","C_received_MWS_comments_date",0,"no_ change","Date Only Picker","Receipt date of review C comments made by Marine Warranty Surveyor","specific_attribute"]
[303,"Engineering","null","null","D_submit_MWS_date",0,"no_ change","Date Only Picker","Submission date for review D to Marine Warranty Surveyor","specific_attribute"]
[304,"Engineering","null","null","D_received_MWS_comments_Date",0,"no_ change","Date Only Picker","Receipt date of review D comments made by Marine Warranty Surveyor","specific_attribute"]
[305,"Engineering","null","null","E_submit_MWS_date",0,"no_ change","Date Only Picker","Submission date for review E to Marine Warranty Surveyor","specific_attribute"]
[306,"Engineering","null","null","E_received_MWS_comments_date",0,"no_ change","Date Only Picker","Receipt date of review E comments made by Marine Warranty Surveyor","specific_attribute"]
[307,"Engineering","null","null","engineering_status",0,"no_ change","Pull Down",null,"specific_attribute","00 - Drawing not issued","01 - Drawing issued for comments","02 - Drawing issued for field","03 - Wainting Asbuilt","04 - Asbuilt Issued"]
[308,"Planning","rundown_curves","null","week_no",0,"no_ change","SYS Short Description Text 255",null,"primary_key"]
[309,"Planning","rundown_curves","null","discipline",0,"no_ change","Pull Down",null,"specific_attribute","Piping fabrication","Piping assembly","Cargo tank paiting","Structures fabrication","Structures assembly","Structure erection","Outfitting fabrication","Outfitting erection","Cable trays assembly","Cables pulling","Connections","Instruments assembly","Hydrotests execution","Piping cleaning reinstatement","Leakage testes execution","Blank/Loop tests execution","Equipment assembly","Painting"]
[310,"Planning","rundown_curves","null","activity",0,"no_ change","SYS Short Description Text 255",null,"specific_attribute"]
[311,"Planning","rundown_curves","null","quantity_total",0,"no_ change","Decimal Amount",null,"specific_attribute"]
[312,"Planning","rundown_curves","null","unit",0,"no_ change","SYS Short Description Text 255",null,"specific_attribute"]
[313,"Planning","rundown_curves","null","plan",0,"no_ change","SYS Short Description Text 255",null,"specific_attribute"]
[314,"Planning","rundown_curves","null","actual",0,"no_ change","Decimal Amount",null,"specific_attribute"]
[315,"Planning","rundown_curves","null","foreseen",0,"no_ change","Decimal Amount",null,"specific_attribute"]
[316,"Planning","rundown_curves","null","accumulated_actual",0,"no_ change","Decimal Amount",null,"specific_attribute"]
[317,"Planning","Physical_S_Curves","null","week_no",0,"no_ change","SYS Short Description Text 255",null,"primary_key"]
[318,"Planning","Physical_S_Curves","null","WBS",0,"no_ change","SYS Short Description Text 255",null,"specific_attribute"]
[319,"Planning","Physical_S_Curves","null","WBS_description",0,"no_ change","SYS Short Description Text 255",null,"specific_attribute"]
[320,"Planning","Physical_S_Curves","null","physical_weight",0,"no_ change","Decimal Amount",null,"specific_attribute"]
[321,"Planning","Physical_S_Curves","null","_baseline_early",0,"no_ change","SYS Short Description Text 255",null,"specific_attribute"]
[322,"Planning","Physical_S_Curves","null","baseline_Later",0,"no_ change","SYS Short Description Text 255",null,"specific_attribute"]
[323,"Planning","Physical_S_Curves","null","actual",0,"no_ change","Decimal Amount",null,"specific_attribute"]
[324,"Planning","Physical_S_Curves","null","foreseen",0,"no_ change","Decimal Amount",null,"specific_attribute"]
[325,"Planning","Financial_S_Curves","null","week_no",0,"no_ change","SYS Short Description Text 255",null,"primary_key"]
[326,"Planning","Financial_S_Curves","null","WBS",0,"no_ change","SYS Short Description Text 255",null,"specific_attribute"]
[327,"Planning","Financial_S_Curves","null","WBS_Description",0,"no_ change","SYS Short Description Text 255",null,"specific_attribute"]
[328,"Planning","Financial_S_Curves","null","financial_weight",0,"no_ change","Decimal Amount",null,"specific_attribute"]
[329,"Planning","Financial_S_Curves","null","baseline",0,"no_ change","SYS Short Description Text 255",null,"specific_attribute"]
[330,"Planning","Financial_S_Curves","null","actual",0,"no_ change","Decimal Amount",null,"specific_attribute"]
[331,"Planning","Financial_S_Curves","null","foreseen",0,"no_ change","Decimal Amount",null,"specific_attribute"]
[332,"Planning","resouce_histogram","null","month_no",0,"no_ change","SYS Short Description Text 255",null,"primary_key"]
[333,"Planning","resouce_histogram","null","discipline",0,"no_ change","SYS Short Description Text 255",null,"specific_attribute"]
[334,"Planning","resouce_histogram","null","construction_site",0,"no_ change","SYS Short Description Text 255",null,"specific_attribute"]
[335,"Planning","resouce_histogram","null","subcontractor",0,"no_ change","SYS Short Description Text 255",null,"specific_attribute"]
[336,"Planning","resouce_histogram","null","onShore_offshore",0,"no_ change","Pull Down",null,"specific_attribute","onshore","offshore"]
[337,"Planning","resouce_histogram","null","type_of_work",0,"no_ change","SYS Short Description Text 255",null,"specific_attribute"]
[338,"Planning","resouce_histogram","null","curve_type",0,"no_ change","SYS Short Description Text 255",null,"specific_attribute"]
[339,"Planning","executive_summary","null","week_no",0,"no_ change","SYS Short Description Text 255",null,"primary_key"]
[340,"Planning","executive_summary","null","significant_activities",0,"no_ change","SYS Short Description Text 255",null,"specific_attribute"]
[341,"Planning","executive_summary","null","attention_points",0,"no_ change","SYS Short Description Text 255",null,"specific_attribute"]
[342,"Planning","programming","null","programming_no",0,"no_ change","SYS Short Description Text 255",null,"primary_key"]
[343,"Planning","programming","null","primavera_P6_activity_ID",0,"no_ change","SYS Short Description Text 255",null,"specific_attribute"]
[344,"Planning","programming","null","man_hour",0,"no_ change","SYS Short Description Text 255",null,"specific_attribute"]
[345,"Planning","programming","null","activity_description",0,"no_ change","SYS Short Description Text 255",null,"specific_attribute"]
[346,"Planning","programming","null","WBS",0,"no_ change","SYS Short Description Text 255",null,"specific_attribute"]
[347,"Planning","programming","null","WBS_description",0,"no_ change","SYS Short Description Text 255",null,"specific_attribute"]
[348,"Planning","programming","null","quantity_total",0,"no_ change","Decimal Amount",null,"specific_attribute"]
[349,"Planning","programming","null","quantity_Unit",0,"no_ change","SYS Short Description Text 255",null,"specific_attribute"]
[350,"Planning","programming","null","Week_Start",0,"no_ change","SYS Short Description Text 255",null,"specific_attribute"]
[351,"Planning","programming","null","Week_Finish",0,"no_ change","SYS Short Description Text 255",null,"specific_attribute"]
[352,"Planning","programming","null","1st_programming",0,"no_ change","SYS Short Description Text 255",null,"specific_attribute"]
[353,"Planning","programming","null","reprogramming",0,"no_ change","SYS Short Description Text 255",null,"specific_attribute"]
[354,"Planning","programming","null","supervisor_name",0,"no_ change","SYS Short Description Text 255",null,"specific_attribute"]
[355,"Planning","programming","item","programming_no",0,"no_ change","SYS Short Description Text 255",null,"foreign_key"]
[356,"Planning","programming","item","item_tag",0,"no_ change","SYS Short Description Text 255",null,"primary_key"]
[357,"Planning","programming","item","WBS",0,"no_ change","SYS Short Description Text 255",null,"specific_attribute"]
[358,"Planning","programming","item","WBS_description",0,"no_ change","SYS Short Description Text 255",null,"specific_attribute"]
[359,"Planning","programming","item","programming_quantity",0,"no_ change","Decimal Amount",null,"specific_attribute"]
[360,"Planning","programming","item","reprogramming_quantity",0,"no_ change","Decimal Amount",null,"specific_attribute"]
[361,"Planning","milestones","null","milestones_no",0,"no_ change","SYS Short Description Text 255",null,"primary_key"]
[362,"Planning","milestones","null","milestone_description",0,"no_ change","SYS Short Description Text 255",null,"specific_attribute"]
[363,"Planning","milestones","null","milestone_type",0,"no_ change","Pull Down",null,"specific_attribute","Control","Contractual"]
[364,"Planning","milestones","null","baseline",0,"no_ change","Date Only Picker",null,"specific_attribute"]
[365,"Planning","milestones","null","actual",0,"no_ change","Date Only Picker",null,"specific_attribute"]
[366,"Planning","milestones","null","foreseen",0,"no_ change","Date Only Picker",null,"specific_attribute"]
[367,"Planning","risk","null","risk_no",0,"no_ change","SYS Short Description Text 255",null,"primary_key"]
[368,"Planning","risk","null","cause",0,"no_ change","SYS Short Description Text 255",null,"specific_attribute"]
[369,"Planning","risk","null","mitigation_plan",0,"no_ change","SYS Short Description Text 255",null,"specific_attribute"]
[370,"Planning","risk","null","responsible",0,"no_ change","SYS Short Description Text 255",null,"specific_attribute"]
[371,"Planning","risk","null","deadline",0,"no_ change","Date Only Picker",null,"specific_attribute"]
[372,"Planning","action_plan","null","action_no",0,"no_ change","SYS Short Description Text 255",null,"primary_key"]
[373,"Planning","action_plan","null","curve",0,"no_ change","Pull Down",null,"specific_attribute","Physical S Curve","Rundown Curve"]
[374,"Planning","action_plan","null","WBS",0,"no_ change","SYS Short Description Text 255",null,"specific_attribute"]
[375,"Planning","action_plan","null","WBS_description",0,"no_ change","SYS Short Description Text 255",null,"specific_attribute"]
[376,"Planning","action_plan","null","justify_deviations",0,"no_ change","SYS Short Description Text 255",null,"specific_attribute"]
[377,"Planning","action_plan","null","action_plan",0,"no_ change","SYS Short Description Text 255",null,"specific_attribute"]
[378,"Planning","action_plan","null","attention_points",0,"no_ change","SYS Short Description Text 255",null,"specific_attribute"]
[379,"Planning","action_plan","null","date_start",0,"no_ change","Date Only Picker",null,"specific_attribute"]
[380,"Planning","action_plan","null","date_finish_",0,"no_ change","Date Only Picker",null,"specific_attribute"]
[381,"Planning","action_plan","null","contract_cost_impact",0,"no_ change","Pull Down",null,"specific_attribute","yes","no"]
[382,"Planning","KPI","null","month_no",0,"no_ change","Date Only Picker",null,"primary_key"]
[383,"Planning","KPI","null","Iprog",0,"no_ change","Decimal Amount","Programming Indicator - Exhibit VI","specific_attribute"]
[384,"Planning","KPI","null","Icprog",0,"no_ change","Decimal Amount","Programming Compliance Indicator - Exhibit VI","specific_attribute"]
[385,"Planning","KPI","null","steel_Structure",0,"no_ change","Decimal Amount","man-hour per ton of assembled steel structure","specific_attribute"]
[386,"Planning","KPI","null","piping_manufactured",0,"no_ change","Decimal Amount","man_hour per ton of manufactured piping","specific_attribute"]
[387,"Planning","KPI","null","piping_assembled",0,"no_ change","Decimal Amount","man_hour per ton of assembled piping","specific_attribute"]
[388,"Planning","KPI","null","structure_painting",0,"no_ change","Decimal Amount","man_hour per square metre of painted steel structure","specific_attribute"]
[389,"Planning","KPI","null","pipe_painting",0,"no_ change","Decimal Amount","man_hour per square metre of painted pipe","specific_attribute"]
[390,"Planning","KPI","null","electrical_cables",0,"no_ change","Decimal Amount","man-hour per metre of laid cable","specific_attribute"]
[391,"Planning","KPI","null","intrumentation_automation_cables",0,"no_ change","Decimal Amount","man-hour per metre of laid cable","specific_attribute"]
[392,"Planning","KPI","null","telecommunications_cables",0,"no_ change","Decimal Amount","man-hour per metre of installed cable","specific_attribute"]
[393,"Planning","KPI","null","electrical_cable_tray",0,"no_ change","Decimal Amount","man-hour per metre of assembled cable tray","specific_attribute"]
[394,"Planning","KPI","null","intrumentation_automation_cables_trays",0,"no_ change","Decimal Amount","man-hour per metre of assembled cable tray","specific_attribute"]
[395,"Planning","KPI","null","telecom_cables_tray",0,"no_ change","Decimal Amount","man-hour per metre of assembled cable tray","specific_attribute"]
[396,"Planning","KPI","null","electrical_connection",0,"no_ change","Decimal Amount","man-hour per connection point","specific_attribute"]
[397,"Planning","KPI","null","instrumentation_automation_connection",0,"no_ change","Decimal Amount","man-hour per connection point","specific_attribute"]
[398,"Planning","KPI","null","telecom_connection",0,"no_ change","Decimal Amount","man-hour per connection point","specific_attribute"]
[399,"Planning","KPI","null","loop_test_of_blank",0,"no_ change","Decimal Amount","man-hour per loop","specific_attribute"]
[400,"Planning","KPI","null","hydrostatic_test",0,"no_ change","Decimal Amount","man-hour per ton of tested pipe","specific_attribute"]
[401,"Procurement","null","null","ID",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[402,"Procurement","null","null","Sub_ID",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[403,"Procurement","null","null","DESCRIPTION",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[404,"Procurement","null","null","PKG_DESCRIPTION",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[405,"Procurement","null","null","Quantity",1,"new","Decimal Amount",null,"specific_attribute"]
[406,"Procurement","null","null","Equipment_Package_Number_(SIGEM)",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[407,"Procurement","null","null","Type_(Super_Critical_/_Critical_/_NA)",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[408,"Procurement","null","null","LLI",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[409,"Procurement","null","null","General_Location",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[410,"Procurement","null","null","Unit_Location",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[411,"Procurement","null","null","Destination_Site",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[412,"Procurement","null","null","SOP",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[413,"Procurement","null","null","SSOP",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[414,"Procurement","null","null","Class_Certification_Type",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[415,"Procurement","null","null","NR_(NR10_/_NR13_/_NA)",1,"new","Pull Down",null,"specific_attribute","NR10","NR13","NA"]
[416,"Procurement","null","null","Inspection_Type_(A_/_B_/_C_-_EXH_V)",1,"new","Pull Down",null,"specific_attribute","A","B","C","NA"]
[417,"Procurement","null","null","INMETRO",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[418,"Procurement","null","null","HS_Code",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[419,"Procurement","null","null","NCM_Code",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[420,"Procurement","null","null","Status_01_(Req/_Purch/_Raw...)",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[421,"Procurement","null","null","Status_02_(In_Advabce_/_On_Date_/_Delayed)",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[422,"Procurement","null","null","EPC_Responsible",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[423,"Procurement","null","null","EPC_Responsible_(Techinical)",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[424,"Procurement","null","null","EPC_Responsible_(Buyer)",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[425,"Procurement","null","null","Required_On_Site_Date_Plan",1,"new","Date Only Picker",null,"specific_attribute"]
[426,"Procurement","null","null","Required_On_Site_Date_Replan",1,"new","Date Only Picker",null,"specific_attribute"]
[427,"Procurement","null","null","MR_Number",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[428,"Procurement","null","null","MR_Last_Revision",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[429,"Procurement","null","null","MR_Date_Plan",1,"new","Date Only Picker",null,"specific_attribute"]
[430,"Procurement","null","null","MR_Date_Replan",1,"new","Date Only Picker",null,"specific_attribute"]
[431,"Procurement","null","null","MR_Date_Actual",1,"new","Date Only Picker",null,"specific_attribute"]
[432,"Procurement","null","null","RFQ\nDATE_PLAN",1,"delete","Date Only Picker",null,"specific_attribute"]
[433,"Procurement","null","null","RFQ\nDATE_ACTUAL",1,"delete","Date Only Picker",null,"specific_attribute"]
[434,"Procurement","null","null","PROPOSAL_RECEIVED_DATE_PLAN",1,"delete","Date Only Picker",null,"specific_attribute"]
[435,"Procurement","null","null","PROPOSAL\nDATE_EXTENSION",1,"delete","Date Only Picker",null,"specific_attribute"]
[436,"Procurement","null","null","PROPOSAL_RECEIVED_DATE_ACTUAL",1,"delete","Date Only Picker",null,"specific_attribute"]
[437,"Procurement","null","null","TBE_Number",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[438,"Procurement","null","null","TBE_Last_Revision",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[439,"Procurement","null","null","TBE_Issue_Date_Plan",1,"new","Date Only Picker",null,"specific_attribute"]
[440,"Procurement","null","null","TBE_Issue_Date_Replan",1,"new","Date Only Picker",null,"specific_attribute"]
[441,"Procurement","null","null","TBE_Issue_Date_Actual",1,"new","Date Only Picker",null,"specific_attribute"]
[442,"Procurement","null","null","TBE_Approval_Date_Plan",1,"new","Date Only Picker",null,"specific_attribute"]
[443,"Procurement","null","null","TBE_Approval_Date_Replan",1,"new","Date Only Picker",null,"specific_attribute"]
[444,"Procurement","null","null","TBE_Approval_Date_Actual",1,"new","Date Only Picker",null,"specific_attribute"]
[445,"Procurement","null","null","PO_Number",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[446,"Procurement","null","null","PO_Last_Revision",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[447,"Procurement","null","null","PO_Issue_Date_Plan",1,"new","Date Only Picker",null,"specific_attribute"]
[448,"Procurement","null","null","PO_Issue_Date_Replan",1,"new","Date Only Picker",null,"specific_attribute"]
[449,"Procurement","null","null","PO_Issue_Date_Actual",1,"new","Date Only Picker",null,"specific_attribute"]
[450,"Procurement","null","null","Estimated_Manufacturing_Lead_Time",1,"new","Decimal Amount",null,"specific_attribute"]
[451,"Procurement","null","null","PO_Delivery_Date_Plan",1,"new","Date Only Picker",null,"specific_attribute"]
[452,"Procurement","null","null","PO_Delivery_Date_Replan",1,"new","Date Only Picker",null,"specific_attribute"]
[453,"Procurement","null","null","PO_Delivery_Date_Actual",1,"new","Date Only Picker",null,"specific_attribute"]
[454,"Procurement","null","null","INCOTERM",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[455,"Procurement","null","null","Transportation_Type",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[456,"Procurement","null","null","Transportation_Time",1,"new","Date Only Picker",null,"specific_attribute"]
[457,"Procurement","null","null","Delivery_On_Site_Time",1,"new","Date Only Picker",null,"specific_attribute"]
[458,"Procurement","null","null","EPC_Responsible_(Expeditor)",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[459,"Procurement","null","null","EPC_Responsible_(Inspector)",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[460,"Procurement","null","null","Supplier",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[461,"Procurement","null","null","Subsupplier",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[462,"Procurement","null","null","Vendor_Responsible",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[463,"Procurement","null","null","Job Title",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[464,"Procurement","null","null","Origin_Area",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[465,"Procurement","null","null","Dimensions_(mm)",1,"new","Decimal Amount",null,"specific_attribute"]
[466,"Procurement","null","null","Weight_(Kg)",1,"new","Decimal Amount",null,"specific_attribute"]
[467,"Procurement","null","null","Special_Tools_(Yes_/_No)",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[468,"Procurement","null","null","KOM_Date_Plan",1,"new","Date Only Picker",null,"specific_attribute"]
[469,"Procurement","null","null","KOM_Date_Replan",1,"new","Date Only Picker",null,"specific_attribute"]
[470,"Procurement","null","null","KOM_Date_Actual",1,"new","Date Only Picker",null,"specific_attribute"]
[471,"Procurement","null","null","LD_Number",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[472,"Procurement","null","null","LD_Last_Revision",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[473,"Procurement","null","null","LD_Issue_Date_Plan",1,"new","Date Only Picker",null,"specific_attribute"]
[474,"Procurement","null","null","LD_Issue_Date_Replan",1,"new","Date Only Picker",null,"specific_attribute"]
[475,"Procurement","null","null","LD_Issue_Date_Action",1,"new","Date Only Picker",null,"specific_attribute"]
[476,"Procurement","null","null","ITP_Number",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[477,"Procurement","null","null","ITP_Last_Revision",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[478,"Procurement","null","null","ITP_Issue_Date_Plan",1,"new","Date Only Picker",null,"specific_attribute"]
[479,"Procurement","null","null","ITP_Issue_Date_Replan",1,"new","Date Only Picker",null,"specific_attribute"]
[480,"Procurement","null","null","ITP_Issue_Date_Actual",1,"new","Date Only Picker",null,"specific_attribute"]
[481,"Procurement","null","null","ITP_Approval_Date_Plan",1,"new","Date Only Picker",null,"specific_attribute"]
[482,"Procurement","null","null","ITP_Approval_Date_Replan",1,"new","Date Only Picker",null,"specific_attribute"]
[483,"Procurement","null","null","ITP_Approval_Date_Actual",1,"new","Date Only Picker",null,"specific_attribute"]
[484,"Procurement","null","null","PIM_Date_Plan",1,"new","Date Only Picker",null,"specific_attribute"]
[485,"Procurement","null","null","PIM_Date_Replan",1,"new","Date Only Picker",null,"specific_attribute"]
[486,"Procurement","null","null","PIM_Date_Actual",1,"new","Date Only Picker",null,"specific_attribute"]
[487,"Procurement","null","null","Fat_Date_Plan",1,"new","Date Only Picker",null,"specific_attribute"]
[488,"Procurement","null","null","Fat_Date_Replan",1,"new","Date Only Picker",null,"specific_attribute"]
[489,"Procurement","null","null","Fat_Date_Actual",1,"new","Date Only Picker",null,"specific_attribute"]
[490,"Procurement","null","null","Inspection_Report_Number",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[491,"Procurement","null","null","Inspection_Report_Last_Revision",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[492,"Procurement","null","null","Inspection_Date_Plan",1,"new","Date Only Picker",null,"specific_attribute"]
[493,"Procurement","null","null","Inspection_Date_Replan",1,"new","Date Only Picker",null,"specific_attribute"]
[494,"Procurement","null","null","Inspection_Date_Actual",1,"new","Date Only Picker",null,"specific_attribute"]
[495,"Procurement","null","null","Expediting_Report_Number",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[496,"Procurement","null","null","Expediting_Report_Last_Revision",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[497,"Procurement","null","null","Expediting_Date_Plan",1,"new","Date Only Picker",null,"specific_attribute"]
[498,"Procurement","null","null","Expediting_Date_Replan",1,"new","Date Only Picker",null,"specific_attribute"]
[499,"Procurement","null","null","Expediting_Date_Actual",1,"new","Date Only Picker",null,"specific_attribute"]
[500,"Procurement","null","null","Vendor_Schedule_Number",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[501,"Procurement","null","null","Vendor_Schedule_Last_Issue_Date",1,"new","Date Only Picker",null,"specific_attribute"]
[502,"Procurement","null","null","%_Vendor_Schedule_Fabrication_Plan",1,"new","Decimal Amount",null,"specific_attribute"]
[503,"Procurement","null","null","%_Vendor_Schedule_Fabrication_Actual",1,"new","Decimal Amount",null,"specific_attribute"]
[504,"Procurement","null","null","IRC_Number",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[505,"Procurement","null","null","IRC_Last_Revision",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[506,"Procurement","null","null","Dispatch_Dossier_Number",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[507,"Procurement","null","null","Dispatch_Dossier_Last_Revision",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[508,"Procurement","null","null","Dispatch_Dossier_Plan_Date",1,"new","Date Only Picker",null,"specific_attribute"]
[509,"Procurement","null","null","Dispatch_Dossier_Issue_Date",1,"new","Date Only Picker",null,"specific_attribute"]
[510,"Procurement","null","null","TRANSPORT_TIME_\n(Days)",1,"new","Decimal Amount",null,"specific_attribute"]
[511,"Procurement","null","null","CUSTOM_CLEARANCE\n(Days)",1,"new","Decimal Amount",null,"specific_attribute"]
[512,"Procurement","null","null","Delivery_On_Site_Date_Plan",1,"new","Date Only Picker",null,"specific_attribute"]
[513,"Procurement","null","null","Delivery_On_Site_Date_Replan",1,"new","Date Only Picker",null,"specific_attribute"]
[514,"Procurement","null","null","Delivery_On_Site_Date_Actual",1,"new","Date Only Picker",null,"specific_attribute"]
[515,"Procurement","null","null","QTY_Delivered",1,"new","Decimal Amount",null,"specific_attribute"]
[516,"Procurement","null","null","RIR_Number",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[517,"Procurement","null","null","RIR_Last_Revision",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[518,"Procurement","null","null","RIR_Issue_Date_Actual",1,"new","Date Only Picker",null,"specific_attribute"]
[519,"C&A","Pipe","Spool","Class",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[520,"C&A","Pipe","Spool","FLUID",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[521,"C&A","Pipe","Spool","INSULATION_THICK_(_mm_)",1,"new","Decimal Amount",null,"specific_attribute"]
[522,"C&A","Pipe","Spool","OPERATION_TEMPERATURE_(_C_)",1,"new","Decimal Amount",null,"specific_attribute"]
[523,"C&A","Pipe","Spool","ELBOW",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[524,"C&A","Pipe","Spool","FLANGE",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[525,"C&A","Pipe","Spool","PIPE_(_m_)",1,"new","Decimal Amount",null,"specific_attribute"]
[526,"C&A","Pipe","Spool","REDUCTION",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[527,"C&A","Pipe","Spool","TEE",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[528,"C&A","Pipe","Spool","VALVE",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[529,"C&A","Pipe","Spool","WELDOLET",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[530,"C&A","Pipe","Spool","OTHER",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[531,"C&A","Pipe","Spool","Fabricated_Weigth_Actual_(kg)",1,"new","Decimal Amount","Actual welding weight fabricated in fabrication site.","specific_attribute"]
[532,"C&A","Pipe","Spool","%_Welding_Fabricated_actual",1,"new","Decimal Amount",null,"specific_attribute"]
[533,"C&A","Pipe","Spool","Released_to_Assembly_Spool_Quantity",1,"new","Decimal Amount",null,"specific_attribute"]
[534,"C&A","Pipe","Spool","%_Released_to_Assembly_Spool",1,"new","Decimal Amount","Number of concluded fabrication spools by spool total.","specific_attribute"]
[535,"C&A","Pipe","Spool","Released_to_Assembly_Spool_Weigth",1,"new","Decimal Amount","Actual assembly welding of isometric spools.","specific_attribute"]
[536,"C&A","Pipe","Spool","Assembly_Weight_(kg)",1,"new","Decimal Amount",null,"specific_attribute"]
[537,"C&A","Pipe","Spool","%_Welding_Assembly",1,"new","Decimal Amount",null,"specific_attribute"]
[538,"C&A","Pipe","Spool","Started_Assembly_Spool_Quantity",1,"new","Decimal Amount",null,"specific_attribute"]
[539,"C&A","Pipe","Spool","Started_Assembly_Spool_Weight",1,"new","Decimal Amount",null,"specific_attribute"]
[540,"C&A","Pipe","Spool","Balance_to_assembly_Spools_quantity",1,"new","Decimal Amount",null,"specific_attribute"]
[541,"C&A","Pipe","Spool","Balance_to_assembly_Spools_weight",1,"new","Decimal Amount",null,"specific_attribute"]
[542,"C&A","Pipe","Spool","%_Spools_released_to_Hidro_test",1,"new","Decimal Amount","Percentual de spools com status no sysweld de igual ou superior a aguardando TH.\n% Spools released to Hidro Test (whaiting HT or up)","specific_attribute"]
[543,"C&A","Pipe","Spool","megablock",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[544,"C&A","Pipe","Spool","Elevation_or_compartment",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[545,"C&A","Pipe","Joint","megablock",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[546,"C&A","Pipe","Support","megablock",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[547,"C&A","Pipe","Support","Elevation_or_compartment",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[548,"C&A","Pipe","Valves","Class",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[549,"C&A","Pipe","Valves","sth",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[550,"C&A","Pipe","Valves","megablock",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[551,"C&A","Pipe","Valves","block_or_module",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[552,"C&A","Pipe","Valves","Elevation_or_compartment",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[553,"C&A","Structure","null","megablock",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[554,"C&A","Structure","Joint","megablock",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[555,"C&A","equipment","null","megablock",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[556,"C&A","equipment","null","data_sheet",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[557,"C&A","equipment","null","location_drawing",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[558,"C&A","equipment","null","foundation_drawing",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[559,"C&A","equipment","null","operation_manual",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[560,"C&A","equipment","null","maintenance_manual",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[561,"C&A","equipment","null","inspection_reports",1,"new","SYS Short Description Text 255","List of inspection reports that may be applied to static or dynamic equipment:\n\n1 - Equipment location topographic survey report\n2 - Internal visual inspection report (SPIE/NR-13)\n3 - Borescope survey report\n4 - Rotating equipment pre alignment inspection report\n5 - Thickness measurement inspection report (SPIE/NR-13)\n6 - Bolt tightening torque inspection report (foundation/structure bolting and flange joint tightening)\n7 - External visual inspection report (SPIE/NR-13)\n8 - Rotating equipment final alignment inspection report\n9 - Mechanical completion inspection report","specific_attribute"]
[562,"C&A","EIT","null","megablock",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[563,"C&A","EIT","null","Elevation_or_compartment",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[564,"C&A","Coating","null","quantity",1,"new","Decimal Amount",null,"specific_attribute"]
[565,"C&A","Coating","null","quantity_unit",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[566,"C&A","Coating","null","surface_preparation_quantity_actual",1,"new","Decimal Amount",null,"specific_attribute"]
[567,"C&A","Coating","null","1st_coating_quantity_actual",1,"new","Decimal Amount",null,"specific_attribute"]
[568,"C&A","Coating","null","2nd_coating_quantity_actual",1,"new","Decimal Amount",null,"specific_attribute"]
[569,"C&A","Coating","null","3th_coating_quantity_actual",1,"new","Decimal Amount",null,"specific_attribute"]
[570,"C&A","Coating","null","4th_coating_quantity_actual",1,"new","Decimal Amount",null,"specific_attribute"]
[571,"Planning","rundown_curves","null","primavera_P6_activity_ID",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[572,"Planning","rundown_curves","null","hull_or_topsides",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[573,"Planning","rundown_curves","null","module_or_block_or_mega_block",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[574,"Planning","Physical_S_Curves","null","primavera_P6_activity_ID",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[575,"Planning","Financial_S_Curves","null","primavera_P6_activity_ID",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[576,"Planning","resouce_histogram","null","baseline",1,"new","Decimal Amount",null,"specific_attribute"]
[577,"Planning","resouce_histogram","null","actual",1,"new","Decimal Amount",null,"specific_attribute"]
[578,"Planning","resouce_histogram","null","foreseen",1,"new","Decimal Amount",null,"specific_attribute"]
[579,"Planning","programming","item","quantity_Unit",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[580,"Planning","programming","item","primavera_P6_activity_ID",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[581,"Planning","action_plan","null","primavera_P6_activity_ID",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[582,"Planning","KPI","null","hull_painting",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[583,"C&A","EIT","null","network_cable_test/certification",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[584,"C&A","EIT","null","NR10",1,"new","Pull Down",null,"specific_attribute","yes","no","NA"]
[585,"C&A","EIT","null","EX",1,"new","Pull Down",null,"specific_attribute","yes","no","NA"]
[586,"C&A","EIT","null","blank_test_report",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[587,"C&A","Pipe","Spool","Fabricated_Weigth_Actual__with_END_aproved",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[588,"C&A","Pipe","Spool","Assembly_Weight_with_END_aproved",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[589,"C&A","Pipe","Spool","Last_status_Date",1,"new","Date Only Picker",null,"specific_attribute"]
[590,"C&A","Pipe","Spool","milestone_description",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[591,"C&A","Pipe","Spool","SHOPDRAWING",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[592,"C&A","Pipe","Spool","CLEANING_METHOD",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[593,"C&A","Pipe","Spool","LEAK_TEST_FOLDER_NUMBER",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[594,"C&A","Pipe","Spool","NACE_(Y/N)",1,"new","Pull Down",null,"specific_attribute","yes","no","NA"]
[595,"C&A","Pipe","Spool","NR13",1,"new","Pull Down",null,"specific_attribute","yes","no","NA"]
[596,"C&A","Pipe","Spool","PMI_report",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[597,"C&A","Pipe","Spool","PMI_date",1,"new","Date Only Picker",null,"specific_attribute"]
[598,"C&A","Pipe","Spool","BOROSCOPE_INSPECTION_report",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[599,"C&A","Pipe","Spool","BOROSCOPE_INSPECTION_date",1,"new","Date Only Picker",null,"specific_attribute"]
[600,"C&A","Pipe","Joint","ISOMETRIC",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[601,"C&A","Pipe","Joint","ISOMETRIC_REVISION",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[602,"C&A","Pipe","Joint","JOINT_TYPE_(FW_PW)",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[603,"C&A","Pipe","Joint","CLASS",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[604,"C&A","Pipe","Joint","FLUID",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[605,"C&A","Pipe","Joint","PIPELINE",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[606,"C&A","Pipe","Joint","Last_status_date",1,"new","Date Only Picker",null,"specific_attribute"]
[607,"C&A","Pipe","Support","SOP",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[608,"C&A","Pipe","Support","SSOP",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[609,"C&A","Pipe","Valves","SOP",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[610,"C&A","Pipe","Valves","SSOP",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[611,"C&A","Pipe","Valves","VALVE_TYPE_(FLG/WLD)",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[612,"C&A","Pipe","Valves","JOINT_NUMBER",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[613,"C&A","Pipe","Valves","FLUID",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[614,"C&A","Pipe","Valves","LEAK_TEST_FOLDER_NUMBER",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[615,"C&A","equipment","null","milestone_description",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[616,"C&A","equipment","null","LOCATION_OF_TAP_AND_TTAS",1,"new","SYS Short Description Text 255",null,"specific_attribute"]
[617,"Safety Studies","null","null","identification",1,"new","Decimal Amount","According to the item 6.17 of I-ET-3000.00-5400-947-P4X-002","primary_key"]
[618,"Safety Studies","null","null","project_phase",1,"new","Pull Down","According to the item 6.17 of I-ET-3000.00-5400-947-P4X-002","specific_attribute"]
[619,"Safety Studies","null","null","description",1,"new","SYS Short Description Text 255","According to the item 6.17 of I-ET-3000.00-5400-947-P4X-002","specific_attribute"]
[620,"Safety Studies","null","null","safety_study_origin",1,"new","SYS Short Description Text 255","According to the item 6.17 of I-ET-3000.00-5400-947-P4X-002","specific_attribute"]
[621,"Safety Studies","null","null","status",1,"new","Pull Down","According to the item 6.17 of I-ET-3000.00-5400-947-P4X-002","specific_attribute"]
[622,"Safety Studies","null","null","deadline",1,"new","Date Picker","According to the item 6.17 of I-ET-3000.00-5400-947-P4X-002","specific_attribute"]
[623,"Safety Studies","null","null","associated_system_sop",1,"new","Decimal Amount","According to the item 6.17 of I-ET-3000.00-5400-947-P4X-002","specific_attribute"]
[624,"Safety Studies","null","null","company_subcontractor_responsible_for_implementation",1,"new","SYS Short Description Text 255","According to the item 6.17 of I-ET-3000.00-5400-947-P4X-002","specific_attribute"]
[625,"Safety Studies","null","null","disciplines_responsible_for_implementation",1,"new","Pull Down","According to the item 6.17 of I-ET-3000.00-5400-947-P4X-002","specific_attribute"]
[626,"Safety Studies","null","null","evidence_of_implementation_or_justification",1,"new","SYS Short Description Text 255","According to the item 6.17 of I-ET-3000.00-5400-947-P4X-002","specific_attribute"]

{"sheet":"C&A - Pipe - Spool","index":2,"n_rows":2,"n_cols":76,"rows_kept":2,"cut":false,"hidden":false,"merged":[[0,6,0,16]]}
[null,null,null,null,null,null,"C&A - Pipe - Spool"]
["hull_or_topsides","block_or_module","site_fabrication","site_assembly","sop","ssop","sth","isometric_number","Isometric_revision","P&ID_no","P&ID_revision","sheet_no","elevation","manufacture","pipe_Line","pipe_system","Spool","piperun","diameter_","thickness","weight","surface_area","internal_coating","internal_coating_type","internal_coating_report","insulation","insulation_type","metal","SPEC_BR","PN","dimensional_report","material_specification","chemical_cleaning","coating_type","coating_report","coating_touchup","status_spool","Class","FLUID","INSULATION_THICK_(_mm_)","OPERATION_TEMPERATURE_(_C_)","ELBOW","FLANGE","PIPE_(_m_)","REDUCTION","TEE","VALVE","WELDOLET","OTHER","Fabricated_Weigth_Actual_(kg)","%_Welding_Fabricated_actual","Released_to_Assembly_Spool_Quantity","%_Released_to_Assembly_Spool","Released_to_Assembly_Spool_Weigth","Assembly_Weight_(kg)","%_Welding_Assembly","Started_Assembly_Spool_Quantity","Started_Assembly_Spool_Weight","Balance_to_assembly_Spools_quantity","Balance_to_assembly_Spools_weight","%_Spools_released_to_Hidro_test","megablock","Elevation_or_compartment","Fabricated_Weigth_Actual__with_END_aproved","Assembly_Weight_with_END_aproved","Last_status_Date","milestone_description","SHOPDRAWING","CLEANING_METHOD","LEAK_TEST_FOLDER_NUMBER","NACE_(Y/N)","NR13","PMI_report","PMI_date","BOROSCOPE_INSPECTION_report","BOROSCOPE_INSPECTION_date"]

{"sheet":"C&A - Pipe - Joint","index":3,"n_rows":2,"n_cols":55,"rows_kept":2,"cut":false,"hidden":false,"merged":[[0,6,0,16]]}
[null,null,null,null,null,null,"C&A - Pipe - Joint"]
["hull_or_topside","block_or_module","P&ID_no","P&ID_revision","sop","ssop","sth","Spool","Joint","diameter_","FW_PW","weld_type","inpection_class","weld_volume","fit_up","1st_repair_report","2st_repair_report","visual","visual__1st_repair","visual__2nd_repair","MT_PT_before_welding","MT_PT_bevel","MT_PT_weld","MT_PT_1st_Repair","MT_PT_2nd_Repair","RT_Paut","RT_Paut_1st_Repair","RT_Paut_2st_Repair","hardness_test","PWHT","PMI","ferrite_test","remark","WPS","heat_1","Lot_1","Heat_2","Lot_2","1st_Consumable","2nd_Consumable","welder_number_root","welder_number_root__1st_repair","welder_number_root__2st_repair","welder_number_buildup","welder_number_buildup_1st_Repair","welder_number_buildup_2st_Repair","status_pipe_joint","megablock","ISOMETRIC","ISOMETRIC_REVISION","JOINT_TYPE_(FW_PW)","CLASS","FLUID","PIPELINE","Last_status_date"]

{"sheet":"C&A - Pipe - Support","index":4,"n_rows":2,"n_cols":17,"rows_kept":2,"cut":false,"hidden":false,"merged":[[0,6,0,16]]}
[null,null,null,null,null,null,"C&A - Pipe - Support"]
["hull_or_topside","block_or_module","site_fabrication","site_assembly","support_tag","pipe_line","spool","isometric_number","Isometric_revision","support_type","manufacture","weight","status_pipe_support","megablock","Elevation_or_compartment","SOP","SSOP"]

{"sheet":"C&A - Pipe - Valves","index":5,"n_rows":2,"n_cols":22,"rows_kept":2,"cut":false,"hidden":false,"merged":[[0,6,0,16]]}
[null,null,null,null,null,null,"C&A - Pipe - Valves"]
["valve","drawing_no","P&ID_no","P&ID_revision","pipe_line","isometric_number","Isometric_revision","manufacture","model_manufacture","diamenter","status_pipe_valves","Class","sth","megablock","block_or_module","Elevation_or_compartment","SOP","SSOP","VALVE_TYPE_(FLG/WLD)","JOINT_NUMBER","FLUID","LEAK_TEST_FOLDER_NUMBER"]

{"sheet":"C&A - Structure","index":6,"n_rows":2,"n_cols":18,"rows_kept":2,"cut":false,"hidden":false,"merged":[[0,6,0,16]]}
[null,null,null,null,null,null,"C&A - Structure"]
["hull_or_topside","block_or_module","structure_type","structure_element","structure_type","drawing_br","drawing_revision","assembly_drawing","assembly_drawing_revision","manufacture_drawing","manufacture_drawing_revision","material_specification","weight","coating_type","coating_report","coating_touchup","status_structure","megablock"]

{"sheet":"C&A - Structure - Joint","index":7,"n_rows":2,"n_cols":21,"rows_kept":2,"cut":false,"hidden":false,"merged":[[0,6,0,16]]}
[null,null,null,null,null,null,"C&A - Structure - Joint"]
["hull_or_topside","block_or_module","structure_element","joint","WW_FW","weld_type","weld_extension","group","inspection_level","WPS","fit_up","visual","PT","MT","RX_US","final_dimensional","welder_number_root","welder_number_buildup","consumable","status_structure_joint","megablock"]

{"sheet":"C&A - equipment","index":8,"n_rows":2,"n_cols":23,"rows_kept":2,"cut":false,"hidden":false,"merged":[[0,6,0,16]]}
[null,null,null,null,null,null,"C&A - equipment"]
["hull_or_topside","block_or_module","sop","ssop","equipment_tag","function_test","manufacturer","model_manufacturer","Elevation_or_compartment","Equipament_Tag","Description_Tag","Drawing_No.","drawing_Revision","status_equipment","megablock","data_sheet","location_drawing","foundation_drawing","operation_manual","maintenance_manual","inspection_reports","milestone_description","LOCATION_OF_TAP_AND_TTAS"]

{"sheet":"C&A - EIT","index":9,"n_rows":2,"n_cols":23,"rows_kept":2,"cut":false,"hidden":false,"merged":[[0,6,0,16]]}
[null,null,null,null,null,null,"C&A - EIT"]
["hull_or_topside","block_or_module","sop","ssop","eit_tag","item_type","quantity","quantity_unit","pullin_cable_report","conection_report","assembly_report","hydrostec_test","calibration_report","continuity_test","megger_test","HIPOT_test","status_eit","megablock","Elevation_or_compartment","network_cable_test/certification","NR10","EX","blank_test_report"]

{"sheet":"C&A - Coating","index":10,"n_rows":2,"n_cols":32,"rows_kept":2,"cut":false,"hidden":false,"merged":[[0,6,0,16]]}
[null,null,null,null,null,null,"C&A - Coating"]
["hull_or_topsides","Mega_block","block_or_module","discipline","item_type","item","painting_system_code_petrobras","painting_system_code_contractor","primary_surface_preparation_report","secondary_surface_preparation_report","painting_report","touchup_report","field_painting_report","surface_preparation_holdpoint_inspection","1st_coating_holdpoint_inspection","2nd_coating_holdpoint_inspection","3rd_coating_holdpoint_inspection","4th_coating_holdpoint_inspection","date_surface_preparation_holdpoint_inspection","date_1st_coating_holdpoint_inspection","date_2nd_coating_holdpoint_inspection","date_3rd_coating_holdpoint_inspection","date_4th_coating_holdpoint_inspection","problems_history","status_coating","quantity","quantity_unit","surface_preparation_quantity_actual","1st_coating_quantity_actual","2nd_coating_quantity_actual","3th_coating_quantity_actual","4th_coating_quantity_actual"]

{"sheet":"Procurement","index":11,"n_rows":2,"n_cols":119,"rows_kept":2,"cut":false,"hidden":false,"merged":[[0,6,0,16]]}
[null,null,null,null,null,null,"Procurement"]
["item_tag","ID","Sub_ID","DESCRIPTION","PKG_DESCRIPTION","Quantity","Equipment_Package_Number_(SIGEM)","Type_(Super_Critical_/_Critical_/_NA)","LLI","General_Location","Unit_Location","Destination_Site","SOP","SSOP","Class_Certification_Type","NR_(NR10_/_NR13_/_NA)","Inspection_Type_(A_/_B_/_C_-_EXH_V)","INMETRO","HS_Code","NCM_Code","Status_01_(Req/_Purch/_Raw...)","Status_02_(In_Advance_/_On_Date_/_Delayed)","EPC_Responsible","EPC_Responsible_(Technical)","EPC_Responsible_(Buyer)","Required_On_Site_Date_Plan","Required_On_Site_Date_Replan","MR_Number","MR_Last_Revision","MR_Date_Plan","MR_Date_Replan","MR_Date_Actual","RFQ\nDATE_PLAN","RFQ\nDATE_ACTUAL","PROPOSAL_RECEIVED_DATE_PLAN","PROPOSAL\nDATE_EXTENSION","PROPOSAL_RECEIVED_DATE_ACTUAL","TBE_Number","TBE_Last_Revision","TBE_Issue_Date_Plan","TBE_Issue_Date_Replan","TBE_Issue_Date_Actual","TBE_Approval_Date_Plan","TBE_Approval_Date_Replan","TBE_Approval_Date_Actual","PO_Number","PO_Last_Revision","PO_Issue_Date_Plan","PO_Issue_Date_Replan","PO_Issue_Date_Actual","Estimated_Manufacturing_Lead_Time","PO_Delivery_Date_Plan","PO_Delivery_Date_Replan","PO_Delivery_Date_Actual","INCOTERM","Transportation_Type","Transportation_Time","Delivery_On_Site_Time","EPC_Responsible_(Expeditor)","EPC_Responsible_(Inspector)","Supplier","Subsupplier","Vendor_Responsible","Job Title","Origin_Area","Dimensions_(mm)","Weight_(Kg)","Special_Tools_(Yes_/_No)","KOM_Date_Plan","KOM_Date_Replan","KOM_Date_Actual","LD_Number","LD_Last_Revision","LD_Issue_Date_Plan","LD_Issue_Date_Replan","LD_Issue_Date_Actual","ITP_Number","ITP_Last_Revision","ITP_Issue_Date_Plan","ITP_Issue_Date_Replan","ITP_Issue_Date_Actual","ITP_Approval_Date_Plan","ITP_Approval_Date_Replan","ITP_Approval_Date_Actual","PIM_Date_Plan","PIM_Date_Replan","PIM_Date_Actual","Fat_Date_Plan","Fat_Date_Replan","Fat_Date_Actual","Inspection_Report_Number","Inspection_Report_Last_Revision","Inspection_Date_Plan","Inspection_Date_Replan","Inspection_Date_Actual","Expediting_Report_Number","Expediting_Report_Last_Revision","Expediting_Date_Plan","Expediting_Date_Replan","Expediting_Date_Actual","Vendor_Schedule_Number","Vendor_Schedule_Last_Issue_Date","%_Vendor_Schedule_Fabrication_Plan","%_Vendor_Schedule_Fabrication_Actual","IRC_Number","IRC_Last_Revision","Dispatch_Dossier_Number","Dispatch_Dossier_Last_Revision","Dispatch_Dossier_Plan_Date","Dispatch_Dossier_Issue_Date","TRANSPORT_TIME_\n(Days)","CUSTOM_CLEARANCE\n(Days)","Delivery_On_Site_Date_Plan","Delivery_On_Site_Date_Replan","Delivery_On_Site_Date_Actual","QTY_Delivered","RIR_Number","RIR_Last_Revision","RIR_Issue_Date_Actual"]

{"sheet":"Engineering","index":12,"n_rows":2,"n_cols":68,"rows_kept":2,"cut":false,"hidden":false,"merged":[[0,6,0,16]]}
[null,null,null,null,null,null,"Engineering"]
["SOP","SSOP","hull_or_topsides","Vendor_name","dicipline_owner","discipline_contractor","operation_MWS","document_type","document_number","document_title","reason_revision","last_issued_revision","last__issued_date","asbuilt_status","3D_model_status","owner_status","classfication_society_status","MWS_status","Final_status","0_issue_planned_date","A_issue_planned_date","B_issue_planned_date","C_issue_planned_date","D_issue_planned_date","E_issue_planned_date","0_issued_date","A_issued_date","B_issued_date","C_issued_date","D_issued_date","E_issued_date","0_submit_owner_date","0_received_owner_comments_date","A_submit_owner_date","A_received_owner_comments_date","B_submit_owner_date","B_receive_owner_comments_date","C_submit_owner_date","C_received_owner_comments_date","D_submit_owner_date","D_received_owner_comments_date","E_submit_owner_date","E_received_owner_comments_date","0_submit_CS_date","0_received_CS_comments_date","A_submit_CS_date","A_received_CS_comments_date","B_submit_CS_date","B_received_CS_comments_Date","C_submit_CS_date","C_received_CS_comments_date","D_submit_CS_date","D_received_CS_comments_Date","E_submit_CS_date","E_received_CS_comments_date","0_submit_MWS_date","0_received_MWS_comments_date","A_submit_MWS_date","A_received_MWS_comments_date","B_submit_MWS_date","B_received_MWS_comments_Date","C_submit_MWS_date","C_received_MWS_comments_date","D_submit_MWS_date","D_received_MWS_comments_Date","E_submit_MWS_date","E_received_MWS_comments_date","engineering_status"]

{"sheet":"Planning - rundown_curves","index":13,"n_rows":2,"n_cols":12,"rows_kept":2,"cut":false,"hidden":false,"merged":[[0,6,0,16]]}
[null,null,null,null,null,null,"Planning - rundown_curves"]
["week_no","discipline","activity","quantity_total","unit","plan","actual","foreseen","accumulated_actual","primavera_P6_activity_ID","hull_or_topsides","module_or_block_or_mega_block"]

{"sheet":"Planning - Physical_S_Curves","index":14,"n_rows":2,"n_cols":9,"rows_kept":2,"cut":false,"hidden":false,"merged":[[0,6,0,16]]}
[null,null,null,null,null,null,"Planning - Physical_S_Curves"]
["week_no","WBS","WBS_description","physical_weight","_baseline_early","baseline_Later","actual","foreseen","primavera_P6_activity_ID"]

{"sheet":"Planning - Financial_S_Curves","index":15,"n_rows":2,"n_cols":8,"rows_kept":2,"cut":false,"hidden":false,"merged":[[0,6,0,16]]}
[null,null,null,null,null,null,"Planning - Financial_S_Curves"]
["week_no","WBS","WBS_Description","financial_weight","baseline","actual","foreseen","primavera_P6_activity_ID"]

{"sheet":"Planning - resouce_histogram","index":16,"n_rows":2,"n_cols":10,"rows_kept":2,"cut":false,"hidden":false,"merged":[[0,6,0,16]]}
[null,null,null,null,null,null,"Planning - resouce_histogram"]
["month_no","discipline","construction_site","subcontractor","onShore_offshore","type_of_work","curve_type","baseline","actual","foreseen"]

{"sheet":"Planning - executive_summary","index":17,"n_rows":2,"n_cols":7,"rows_kept":2,"cut":false,"hidden":false,"merged":[[0,6,0,16]]}
[null,null,null,null,null,null,"Planning - executive_summary"]
["week_no","significant_activities","attention_points"]

{"sheet":"Planning - programming","index":18,"n_rows":2,"n_cols":13,"rows_kept":2,"cut":false,"hidden":false,"merged":[[0,6,0,16]]}
[null,null,null,null,null,null,"Planning - programming"]
["programming_no","primavera_P6_activity_ID","man_hour","activity_description","WBS","WBS_description","quantity_total","quantity_Unit","Week_Start","Week_Finish","1st_programming","reprogramming","supervisor_name"]

{"sheet":"Planning - programming - item","index":19,"n_rows":2,"n_cols":8,"rows_kept":2,"cut":false,"hidden":false,"merged":[[0,6,0,16]]}
[null,null,null,null,null,null,"Planning - programming - item"]
["programming_no","item_tag","WBS","WBS_description","programming_quantity","reprogramming_quantity","quantity_Unit","primavera_P6_activity_ID"]

{"sheet":"Planning - milestones","index":20,"n_rows":2,"n_cols":7,"rows_kept":2,"cut":false,"hidden":false,"merged":[[0,6,0,16]]}
[null,null,null,null,null,null,"Planning - milestones"]
["milestones_no","milestone_description","milestone_type","baseline","actual","foreseen"]

{"sheet":"Planning - risk","index":21,"n_rows":2,"n_cols":7,"rows_kept":2,"cut":false,"hidden":false,"merged":[[0,6,0,16]]}
[null,null,null,null,null,null,"Planning - risk"]
["risk_no","cause","mitigation_plan","responsible","deadline"]

{"sheet":"Planning - action_plan","index":22,"n_rows":2,"n_cols":11,"rows_kept":2,"cut":false,"hidden":false,"merged":[[0,6,0,16]]}
[null,null,null,null,null,null,"Planning - action_plan"]
["action_no","curve","WBS","WBS_description","justify_deviations","action_plan","attention_points","date_start","date_finish_","contract_cost_impact","primavera_P6_activity_ID"]

{"sheet":"Planning - KPI","index":23,"n_rows":2,"n_cols":20,"rows_kept":2,"cut":false,"hidden":false,"merged":[[0,6,0,16]]}
[null,null,null,null,null,null,"Planning - KPI"]
["month_no","Iprog","Icprog","steel_Structure","piping_manufactured","piping_assembled","structure_painting","pipe_painting","electrical_cables","intrumentation_automation_cables","telecommunications_cables","electrical_cable_tray","intrumentation_automation_cables_trays","telecom_cables_tray","electrical_connection","instrumentation_automation_connection","telecom_connection","loop_test_of_blank","hydrostatic_test","hull_painting"]

{"sheet":"Safety Studies","index":24,"n_rows":2,"n_cols":10,"rows_kept":2,"cut":false,"hidden":false,"merged":[[0,6,0,16]]}
[null,null,null,null,null,null,"Safety Studies"]
["identification","project_phase","description","safety_study_origin","status","deadline","associated_system_sop","company_subcontractor_responsible_for_implementation","disciplines_responsible_for_implementation","evidence_of_implementation_or_justification"]

{"sheet":"Standardized Color for 3D Model","index":25,"n_rows":80,"n_cols":17,"rows_kept":80,"cut":false,"hidden":false,"merged":[[74,1,78,1],[45,1,46,1],[47,1,48,1],[49,1,62,1],[64,1,65,1],[66,1,70,1],[72,1,73,1],[0,12,0,13],[0,15,0,16],[42,1,43,1],[0,0,0,1],[0,3,0,4],[0,6,0,7],[0,9,0,10],[2,1,6,1],[3,7,4,7],[3,16,6,16],[7,1,39,1],[7,16,8,16]]}
["C&A - Pipe - Spool",null,null,"C&A - Pipe - Valves",null,null,"C&A - Structure",null,null,"C&A - equipment",null,null,"C&A - EIT",null,null,"C&A - Coating"]
["Status","Color",null,"Status","Color",null,"Status","Color",null,"Status","Color",null,"Status","Color",null,"Status","Color"]
["00 - WS - Spool Canceled","Fabrication not started",null,"00 - Not received","Not received",null,"00 - Not Started","Fabrication not Started",null,"00 - Not received","Not received",null,"00 - Not received","Not received",null,"00 - Waiting Surface Preparation","Not Started"]
["01 - WS - Spool Hold",null,null,"01 - Assembly not started","Released to assembly",null,"01 - Wainting Manufacture","Fabrication",null,"01 - Assembly not started","Released to assembly",null,"01 - Assembly not started","Released to assembly",null,"01 - Waiting First Coating","Painting"]
["02 - WS - Waiting for material",null,null,"02 - Assembled Valve","Assembled and released",null,"02 - Waiting Painting",null,null,"02 - Waiting Inspection","Inspection",null,"02 - Waiting Inspection","Inspection",null,"02 - Waiting Second Coating"]
["03 - WS - Not Allocated",null,null,null,null,null,"03 - Assembly not started","Released to assembly",null,"03 - Assembled Equipment","Assembled and Released",null,"05 - Assembled Item","Assembled and Released",null,"03 - Waiting Third Coating"]
["04 - WS - Not Started",null,null,null,null,null,"04 - Waiting Welding","Assembly",null,null,null,null,null,null,null,"04 - Waiting Fourth Coating"]
["05 - WS - Waiting Coupling","Fabrication",null,null,null,null,"05 - Waiting Inspection","Inspection",null,null,null,null,null,null,null,"05 - Wainting Surface Preparation Field","Field Painting"]
["06 - WS - Waiting Material List Registration",null,null,null,null,null,"06 - Assembled Structure","Assembled and released",null,null,null,null,null,null,null,"06 - Waiting Field Painting"]
["07 - WS - Wainting for Alloy Identification",null,null,null,null,null,null,null,null,null,null,null,null,null,null,"07 - Wainting Inspection Field","Field Inspection"]
["08 - WS - Wainting Welding",null,null,null,null,null,null,null,null,null,null,null,null,null,null,"08 - Coating Approved","Painted and Released"]
["09 - WS - Waiting PT 1st Repair"]
["10 - WS - Waiting PT 2nd Repair"]
["11 - WS - Waiting Welding  1st Repair"]
["12 - WS - Waiting Welding  2nd Repair"]
["13 - WS - Waiting Visual"]
["14 - WS - Waiting Visual  1st Repair"]
["15 - WS - Waiting Visual -2nd Repair"]
["16 - WS - Wainting  Approval Threaded/Glued Joint "]
["17 - WS - Wainting PT/MT"]
["18 - WS - Wainting PT before PWHT"]
["19 - WS - Wainting  RT/Paut"]
["20 - WS - Wainting  hardness test"]
["21 - WS - Wainting PWHT"]
["22 - WS - Wainting hardness  after PWHT"]
["23 - WS - Wainting PT after PWHT"]
["24 - WS - Wainting RT/Paut after PWHT"]
["25 - WS - Wainting tightness"]
["26 - WS - Wainting ferrite test"]
["27 - WS - Wainting traceability TAG"]
["28 - WS - Wainting dimensional"]
["29 - WS - Wainting Hydrostatic test"]
["30 - WS - Wainting for painting condition definition"]
["31 - WS - Wainting Metallization"]
["32 - WS - Wainting Metallization/Coating"]
["33 - WS - Wainting Coating/Painting"]
["34 - WS - Wainting electroplating"]
["35 - WS - Wainting iron-blast/Primer"]
["36 - WS - Wainting Intermediate Painting"]
["37 - WS - Wainting  Painting finishing"]
["38 - Assembly not started","Released to assembly"]
["39 - C&A - Wainting Coupling","Assembly"]
["40 - C&A - Wainting Material List Registration","Inspection"]
["41 - C&A - Wainting Alloy Identification"]
["42 - C&A - Wainting Welding","Assembly"]
["43 - C&A - Waiting PT 1st Repair","Inspection"]
["44 - C&A - Waiting PT 2nd Repair"]
["45 - C&A - Wainting Welding 1st Repair","Assembly"]
["46 - C&A - Wainting Welding 2nd Repair"]
["47 - C&A - Wainting Visual","Inspection"]
["48 - C&A - Wainting Visual 1st Repair"]
["49 - C&A - Wainting Visual 2nd Repair"]
["50 - C&A -   Approval Threaded/Glued Joint "]
["51 - C&A - Wainting PT/MT"]
["52 - C&A - Wainting PT before PWHT"]
["53 - C&A - Wainting RT/Paut"]
["54 - C&A - Wainting hardness test"]
["55 - C&A - Wainting PWHT"]
["56 - C&A - Wainting hardness test after PWHT"]
["57 - C&A - Wainting PT after PWHT"]
["58 - C&A - Wainting RT/Paut after PWHT"]
["59 - C&A - Wainting tighness"]
["60 - C&A - Wainting thickness measurement"]
["61 - C&A - Wainting support joint","Assembly"]
["62 - C&A - Wainting traceability","Inspection"]
["63 - C&A - Wainting field dimensional"]
["64 - C&A - Wainting Metallization","Coating"]
["65 - C&A - Waiting for Metalization/Coating"]
["66 - C&A - Waiting for Coating/Painting"]
["67 - C&A- Waiting for Galvanization"]
["68 - C&A - Waiting for painting"]
["69 - C&A - Waiting for Support","Welded"]
["70 - C&A - Waiting for Hydrostatic test","Hidrostatic test and Washing"]
["71 - C&A - Waiting for Washing"]
["73 - C&A - Waiting for Accessories","Welded"]
["73 - C&A - Waiting for Painting touch"]
["74 - C&A - Waiting Thermal Insulation"]
["75 - C&A - Waiting for conditioning "]
["76 - C&A - Waiting for Documentation"]
["77 - C&A - Spool Assembled and Released","Assembled and released"]