EXHIBIT VI - APPENDIX 2

LIST OF CONTROL MILESTONES

FPSO PETROBRAS 91 (P-91)

************Revision Control*************

Rev 0: Bid original version

SUMMARY

1	OBJECTIVE	3

2	CONTROL MILESTONES	3

2.2	MOBILIZATION	3

2.3	DETAIL ENGINEERING	3

2.4	ACQUISITIONS	4

2.5	HULL FABRICATION	4

2.6	TOPSIDES FABRICATION	4

2.7	INTEGRATION	5

2.8	OFFSHORE	6

# OBJECTIVE

- This document aims to establish a preliminary list of milestones to be contemplated by SELLER in the preparation of the Detail Project Schedule.

- The list of milestones established in this Appendix may be supplemented during the Agreement when requested by BUYER or SELLER.

# CONTROL MILESTONES

  - Control Milestones described in this appendix must be implemented in all PBS deliverables that have activities related to the milestone.

# MOBILIZATION

    - Mobilization of the Managing Staff: Finish of mobilization of managers, coordinators and discipline leaders.

    - Functional Engineering Office: Finish of the implementation of the Engineering office.

    - Functional work site: Finish of the implementation of the work site.

# DETAIL ENGINEERING

    - Start of Detail Engineering: Issuance of the first list of documents related to the Executive Project

    - Finish of SSOPs list: Issuance of the Operating Sub Systems list (SSOPs) and Precedence Network, according to Exhibit IX.

    - Finish of P&IDs issuance: According with definitions in Appendix 1 of Exhibit XI

    - Finish of Piping Isometric issue with flexibility study: According with definitions in Exhibit XI

    - Finish of documentation issuance the superstructures and pipe-racks: Issuance of the last document referring to the detailed design of superstructures and pipe-racks for construction.

    - Finish of isometric drawing issuance for piping fabrication and assembly: Issuance of the last piping isometric drawing.

    - Issuance of the electrical charges list with typical functional diagram: Issuance of the first electrical Charges list with the typical functional diagram.

    - Finish of the design of Typical Instrumentation Details: Issuance of the last document referring to the typical detailing of the instruments defined in the Detail Project.

    - Issuance of the List of I/O and Loop Diagrams: It characterizes the delivery of the last Detail Project document for I/O and loop diagram released for construction.

    - Finish of the issuance of Technical Evaluation of Mechanical Equipment: Issuance of the last technical evaluation of mechanical equipment.

    - Finish of 30% Design Review of the 3D Model: Approval of 30% Design Review and databases delivery of CAE tools with 60% maturity

    - Finish of 60% Design Review of the 3D Model: According with definitions in Appendix 1 of Exhibit XI

    - Finish of 90% Design Review of the 3D Model: According with definitions in Appendix 1 of Exhibit XI

    - Finish of the Detail Project: Issuance of all drawings of the Detail Project for construction and other technical documents, except for As-Built, Databooks and Technical Advisory documents.

    - Finish of the issuance of As-Built Documentation: Issuance of the last As-Built design.

    - Finish of Databook issue: Issuance of the last Databook.

# ACQUISITIONS

    - Issuance of purchase order for Critical Equipment TAG-1…N: Issuance of the purchase/authorization request of the Critical Equipment TAG-1 … N.

    - Issuance of supplier fabrication documentation for Critical Equipment Supplier TAG-1…N: Issuance of the necessary documentation for start fabrication of Critical Equipment TAG-1 …N.

    - Receipt of Critical Equipment TAG-1…N in the site: Receiving of the Critical Equipment TAG 1 …N at yard of equipment assembly.

# HULL FABRICATION

    - Start of Hull construction (Hull strike steel): According with definitions Appendix 1 of Exhibit XI.

    - Hull keel laying: According with definitions in Appendix 1 of Exhibit XI.

    - Hull float off: According with definitions in Exhibit XI

# TOPSIDES FABRICATION

    - Start of Module Assembly 1...N: Cutting of the first plate, including dimensional inspection report issuance

    - Finish of Module Assembly 1...N: Finish of all assembly activities with Mechanical Completion Certificated

    - Finish of superstructures and pipe-racks construction: Finish of superstructures and pipe-racks construction, with all the quality reports issued.

    - Start of piping fabrication: Finish of first spools fabrication, with all quality reports issued.

    - Finish of piping fabrication: Finish of last spool fabrication, with all quality reports issued.

    - Start of piping assembly: Assembly of the first piping spool, including emission of dimensional inspection report and welding of this spool.

    - Finish piping assembly: Finish of piping assembly, including the issuance of dimensional inspection and welding report.

    - Start of piping hydrotests: Finish of the first set of 10 approved and documented hydrostatic tests.

    - Finish of the Critical Equipment TAG-1…N assembly: Finish of the assembly of the Critical Equipment TAG-1...N, with all quality reports issued.

    - Finish of electric and Instrumentation cable trays assembly: Finish of the assembly of electrical and instrumentation trays, when the respective quality reports are already issued.

    - Finish of electrical and instrumentation cables laying: Finish of electrical and instrumentation cables laying, with the respective quality reports issued.

# INTEGRATION

    - Arrival of Hull at the Integration Shipyard: Hull mooring at Integration Shipyard.

    - Arrival of each module at the Integration Shipyard: Load out of each module at the Integration Shipyard

    - Lifting of the first Topsides Module: According with definitions in Appendix 1 of Exhibit XI

    - Last topsides module lifting: According with definitions in Appendix 1 of Exhibit XI

    - Finish of Leak test onshore: Issuance of the latest onshore leak test report.

    - Start of Plant Simulation: Start filling systems with water for Plant Simulation

    - Issuance of NR-10 documentation: Issuance of all the necessary documentation complying with NR-10 standard.

    - Issuance of NR-13 documentation: Issuance of all the necessary documentation complying with NR-13 standard.

    - Finish of Modules Integration: Finish of all integration scope, including the issuance of quality reports.

    - Departure from the Integration Shipyard: Completion of all integration activities in the Integration Shipyard.

    - Substantial Completion: According with definitions in Appendix 1 of Exhibit XI

# OFFSHORE

    - Final FPSO location moored: Finish FPSO mooring in the final location

    - FPSO ready for Pull-in: FPSO Offshore ready to start the first riser Pull-in

    - Start of First oil: the day of the first oil production well opening

    - Start of First Gas Reinjection: the day of the first gas reinjection at well

    - Start of Flare Out: the day of the Flare Out

    - Start of First Offloading: the day of the first offloading operation

    - Start of Fuel Gas Consumption at Turbogenerator: the day of the first turbogenerator running continuously with fuel gas

    - Start of Steam Turbine Generator: the day of the steam turbine generator running continuously, if applicable

    - Start of Gas Treatment (CO2 Removal): the day of the first gas treatment (CO2 Removal) operation

    - Start of Gas Export: the day of the first gas export operation

    - Start of Water treatment: the day of the first water treatment operation

    - Start of Water Injection: the day of the first water injection at well