## APPENDIX 1
FPSO - _________________________________________________
ANEXO A - PE-1PBR-01253 - AVALIAÇÃO PARA ACEITAÇÃO PRELIMINAR DA UEP AFRETADA
EXHIBIT VIII - APPENDIX 1
***********Revision Control*********** 0: Bid original version
ITEM | DISCIPLINE | SYSTEM (SOP) | DESCRIPITION
1 | General | On-shore N2/He Leak Test | SELLER shall perform cryogenic nitrogen/helium (N2He) leakage tests to ensure tightness in all hydrocarbon systems and high-pressure water injection system prior to sail-away of the Unit from integration yard. Systems to be N2He leakage tested are at least the following ones: multiphase process fluid system, oil system up to stabilization, process gas system, produced water system, closed drain system, HP/LP/Cold flare system, HP/LP fuel gas system, condensate gas system, fiscal/offloading metering systems, well service pumps systems (including service header), seal gas conditioning skids/panels, gas and CO2 compression system. Leakage Tests shall encompass all flanges, valves (stems, bonnets, relief plugs), clamp type connections (gray-locks), threaded connections, instrument tubing/manifolds, vessels, exchangers, including vendor skids/panels. After the conclusion of N2He leak test campaign and before sail-away of integration yard, SELLER shall perform the so-called “final sweep test” (which can be performed using N2 only) in order to reduce the number of witness joints and also kill additional leaks imposed by commissioning activities. The sweep test scope is the following: (i) Oil path for the first and second production wells; (ii) Gas injection Path for the First and Second wells; (iii) One compressor train (each type); (iv) Gas dehydration, Fuel Gas and CO2 removal path and (v) Gas lift path for the first well if this is critical for ramp up. (vi) The N2 “sweep tests” shall be performed with the piping systems in its final condition, i.e., without breaking torque of any mechanical joints (flanges or hubs), and with process instrumentation aligned. The sweep test pressure shall be the maximum allowed pressure for lines package/system and the settle out pressure for compression systems. SELLER shall keep control and identification of all “witness joints” on the course of the N2He leakage test campaign. All witness joints shall be tagged in the field after N2He leakage test being performed. “Witness joints” are considered mechanical joints (flanged or hubs/clamped) or tubing/instrument connections which had to be broken after leak test approval or the ones which were not able to be tested during leak test (such as boundary limits with temporary flanges). During the N2 sweep test SELLER shall reduce number of witness joints as low as possible, and report it to PETROBRAS. The remaining witness joints shall be monitored in loco during start up or offshore commissioning with process fluid.
2 | Marine | Offloading System | (i) Visual verification of all equipment arrangement to check are free of obstructions; (ii) Functional test of Hose Reel to check there is no obstructions / clashing during Pay-in/Pay-out; (iii) Functional Pay-out/Pay-in test of the offloading hose full of water including break check; (iv) Hydrotest of Hose including to check integrity of Reel end flange connections and swivel integrity; (v) Check Emergency Offloading System and check proper handling means are available to install the hose if necessary, and the correct alignment between the flange and the ramp; (vi) Check of infra-red camera to monitor offloading leakage; (vii) Check if way of messenger line are free of obstructions; (viii) Check the hose reel not contain sharp edges or any other part or structure that could damage the hose’s cover; (ix) For pull in and pull out operations check if all padeye and all other accessories are properly installed.
3 | Marine | Cargo System, Off-Spec Oil, Off-Spec Water, Slops tanks | (i) All tanks painted, cleaned and closed (ii) Functional Test of all pumps with water (iii) Stagger Test of all tanks concluded
4 | Marine | Hawser system for offloading operation | (i) Visual verification of all equipment arrangement to check possible obstructions; (ii) Functional test of quick release; (iii) Calibration of quick release mechanism. (iv) Check if the hawser permanently attached to a chain stopper;
5 | Marine | Machinery Bilge Treatment System & Slop Water Treatment Discharge System | (i) Functional Test of the system; (ii) Check Slop Treatment Unit and TOG Analyser commissioning and operability; (iii) Run / function test of treatment plant, simulate high oil content and check overboard discharge will be avoided.
6 | Marine | ICCP | (i) All units shall be functional.
7 | Marine | Marine Growth Prevention Systems | (i) Function test for Hypochlorite/Chlorination System. (ii) Check hypochlorite supply for each injection point (SWLP, Ballast sea chest, FWD Fire pump etc).
8 | Marine | Sewage Unit | (i) Check system operability, (ii) Perform sample collection and analysis upstream and downstream for certify compliance with IBAMA and CONAMA requirements as per sampling procedure. (iII) Check flowmeter to overboard (grey and black water)
9 | Marine | IGG & Deck Seal SW Pumps | (i) IGG system functional test; (ii) Verify the specified oxygen content is being met; (iii) Verify the O2 analyser certification/calibration; (iv) Functional test of deck seals pumps (v) air Built up pressure to the tanks.
10 | Marine | Accomodation Block and habitation | (i) Verification all facilities are avaialble in Petrobras cabins, offices and meeting room as per GTD; (ii) Check potable water tank cleanliness and water potability (ANVISA requirement) (iII) check existence and location of chlorination injection and sampling points to comply with ANVISA requirements.
11 | Marine | Bunkering Stations | (i) Function test bunkering reel, hose and connections. (ii) Pay-out and Hydrotest of the hose to ensure no leakages
12 | Marine | Pull-in | (i) Pull-out test using the main winch with 90% of winch nominal capacity; (ii) Functional test of all main & auxiliary riser pull-in winch (main and auxiliary) travelling over all slot positions; (iii) Verify if all auxiliary cables for auxiliary sheaves are prepared with no interferences clashing in all slot positions; (iv) Functional test of Trolley Sheave traveeling and docking at all slots positions. After that position the trolley sheave; docked at the first oil slot. (v) Function test of overhead crane and travel across the entire distance from aft to fwd (vi) Check if have spare wire rope as per GTD;
13 | Mooring | Mooring System | (i) Functional test of all Chain Jacks and chain stoppers. Keep the installation chain passed and ready on the position that will start mooring hook-up operation; (ii) Function test of the chain handling skidding system, travelling across each mooring chain position. (ii) Check no obstsructions, no clashs, no leaks; (iii) Install all installation chains and messenger cables; (iv) Function test of mooring line load cell read outs at local and remote stations (CCR) (v) Check the Unit is prepared to connect Petrobras Positioning Boats
14 | Marine | On-shore Full Load Test (Hull and Emergency Generators) | (i) Full Load test in Emergency, Essentials generators in accordance with commissioning procedure endorsed by Vendors and Classification Society; (ii) Test of synchronization and load transfer of Emerg x Essentials Generators and endurance; (iii) Simulate a F&G alarms at engine run to check Essential shutdown and emergency start-up; (iv) Black Start-up test to be performed (v) UPS fault simulation and Emergency Generator Start-Up test (vi) Test consecutive starts as design specifications, for each start-up source (battery, hydraulic or pneumatic)
15 | Topside Facilities | On-shore Full Load Test (Turbogenerators and Steam Turbine Generators if applicable) | (i) Full Load test Gas Turbine Generators in accordance with commissioning procedure endorsed by Vendors and Classification Society obs: The Steam Turbine Generator shall be tested at least with 20% of its maximum output capacity. Classification Society acknowledgement shall be obtained if applicable. (ii) Sinc Tests (load acceptance and load rejection), load sharing and load shading (PMS) completed. (iii) Simulate a F&G alarms to check GTGs shutdown and immediate essential gen start-up. (iv) Test of synchronization and load transfer of Emerg x Essentials Generators and endurance (v) Black Start-up test to be performed (vi) Water Mist Discharge in all Turbines.
16 | Topside Facilities | Instrument Air | (i) Run / Functional test of Compressor (ii) Run / function test of Air Dryer and verify dew point (iii) Check if System is Pressurized with Air for all consumers with no condensation .
17 | Topside Facilities | Nitrogen | (i) Functional test of the system (generators and compressors) (ii) Check if System is Pressurized with Nitrogen for all consumers (high and low pressure) with no condensation
18 | Topside Facilities | Cranes | Running tests are done to demonstrate that the crane performs as per the specification. The tests enable the purchaser to confirm primarily that: (i) the crane performance is satisfactory; (ii) the controls operate correctly; (iii) there are no leaks or other faults; (iv) the crane can operate continuously, under load, as anticipated on site; (v) confirm the limit switch function of Winch Payout Limit – main fall, including visual and audible alarms; (vi) confirm the limit switch function of Winch Payout Limit – auxiliary fall, including visual and audible alarms; (vii) confirm the limit switch function of Anti Two-Block – main fall, including visual and audible alarms. (viii) confirm the limit switch function of Anti Two-Block – auxiliary fall, including visual and audible alarms; (ix) check and verify the boom is limited from movements to restricted zones; (x) confirm the window wipers function is clearing a minimum of 80 % of the screen area; (xi) check and verify air conditioning operate correctly; (xii) check and verify Emergency lowering operate correctly; (xiii) check and verify no potential dropped object hazard - prevent snagging e.g. lights, anemometers, horns, loud-speakers. (xiv) Functional test of the cranes (xv) Verification if the Operational Sector (shadown area) is implemented. Documentation: (i) Lifting equipment test certificate; (ii) Site acceptance test (SAT) and FAT (factory acceptance test). (iii) Baseline data and settings have been recorded for future operations and maintenance use.
19 | Topside Facilities | Cooling Medium | (i) Functional Test of all cooling water pumps including seal system; (ii) Lab test to check quality parameters were achieved; (iii) Visual line walk to check if whole system free of leakages; (iv) System Pressurized with Nitrogen.
20 | Topside Facilities | Heating Medium | (i) Functional Test of all cooling water pumps including seal system; (ii) Lab test to check quality parameters were achieved; (iii) Visual line walk to check if whole system free of leakages; (iv) System Pressurized with Nitrogen. (v) Check operability of WHRU control valves and dampers
21 | Topside Facilities | Sea Water Lift | (i) Pressurize the header (water filling ) to check if whole system free of leakages. (ii) Functional Test of all pumps in open circuit to overboard including hydraulic oil lubrication system;
22 | Topside Facilities | Well Service Pumps | (i) Perform functional recycle tests in all pumps using fresh water. Pressure shall be increade in steps up to maximum operation pressure; (ii) Check coflexip support availability as per GTD.
23 | Topside Facilities | Riser Leak Test Pumps | (i) Perform functional recycle tests in all pumps using fresh water. Pressure shall be increade in steps up to maximum operation pressure.
24 | Topside Facilities | Chemical Injection | (i) Functional test of all pumps to check if fresh water achieves the expected injection points; (ii) Check storage tanks cleanness. (iii) Check correct tubing identification in TUTU plate for subsea chemicals (iv) Check the Filling Station: the hoses and connections integrity, hoses and lines with the correct chemicals product identification.
25 | Topside Facilities | Fresh Water Generation for Topsides | (i) Function test of R.O feed pumps and R.O package. (ii) Check RO water analysis and flow rates.
26 | Topside Facilities | Riser Filling Fresh Water and Diesel | (i) Functional Test of all pumps and check if design pressure has achieved close to the well service pump suction.
27 | Safety | Open Drain (Topsides) | (i) Check topside drains & scuppers as well as all headers and branches are properly cleaned without obstructions or valves blocking the drainage system; (ii) Functionality tests to be performed during deluge tests for all modules. Any overflow (over spilling gutters, penetrations collars etc) from pankake to main deck will not be accpetable; (iii) Reports to be made available (ANP-SGSO);
28 | Topside Facilities | CCR HMI | (i) Check Supervisory System and functionality of operator stations at CCR.
29 | Topside Facilities | Topsides Electrochlorination | (i) Perform Functional test on the skid and check chloride design parameters were achieved.
30 | Topside-Oil | On-Shore Plant Simulation (Oil System) | Perform Process Onshore Oil Plant Simulation Functional Test up to operation pressure, with fresh water and nitrogen in closed circuit circulation to check the following requirements: (a) Verification of the first oil flow path functionality; (b) All major process variable control loops (level, pressure, flow) are functional, no blockages in the first oil flow path, no major passing of Pressure Control Valves to Flare (PCV's) that would result in impossible pressure control, no major passing of Level Control Valves to downstream equipment (LCV's) that would result in impossible level control, no major passing of Flow Control Valves to downstream equipment (FCV's) that would result in impossible flow control, all BDV's on the first oil flow path are holding the N2 pressure in the respective pressure vessels, all NRV´s in the oil path are correctly installed in the correct flow direction, all NRV's returns are holding to allow for example intervention on crude crude exchanger inlet header and crude oil heater inlet header, all major equipment isolation valves are holding to identify issues that could only be resolved by total production shutdown later on after HC in milestone, no N2 migration to other gas systems due to passing SDV's is present which could not be managed after HC in milestone, no significant issue related to any operability or equipment start up issues that would represent a concern that could impact FPSO performance and uptime when operating with hydrocarbons, no false valve position indicators for the manual valves i.e. open is actual physically closed, no passing througout closed drain valves concluding in gradual build up of closed drain vessel level. Obs1 - Water needed throughout the closed circuit simulation can be sourced from a Off-Oil/Water tank using the existing tank submerged pumps. Obs2 - Manifolds are not required to be in the test. Obs3 - Test Separator & Pumps Functional test of all pumps including seal system.
31 | Topside-Oil | Pig Launchers and Receivers | (i) Check all Pig launchers and Receivers are functional (ii) N2He test for all pig launchers and receivers to ensure no leaks including the doors check
32 | Topside-Oil | Manifold | (i) Functional Test all all chokes valves; (ii) Check chokes (production and test headers) stroke test and calibration (0 to 100% position). From 0 to 30%, increase the opening step wisely in 0,5%;
33 | Topside-Oil | Closed Drain Drum & Pumps | (i) Functional Test of all pumps including seal system. (ii) Check vessel instumentation
34 | Topside-Gas | Main Gas Compression System | (i) N2He Leak Test packages concluded in suction, interastage, discharge. (ii) N2 Closed Circuit Coupled Run in all trains. Contractor is requested not to remove inlet / out pipes from compressor and not to remove coupling (Gear Box x Electrical Motor x Compressor) after conclusion of N2 Closed Circuit test (iii) Reinstallation of piping system after item (i) (iv) Check all major process variable control loops (level, temperature, pressure, minimum flow - surge) of the Compression Plant are functional. (v) Functional and logic test for all SDVs, XVs and BDVs of the Compression Plant.
35 | Topside-Gas | Export Gas Compression System | (i) N2He Leak Test packages concluded in suction, interastage, discharge. (ii) N2 Closed Circuit Coupled Run in all trains. Contractor is requested not to remove inlet / out pipes from compressor and not to remove coupling (Gear Box x Electrical Motor x Compressor) after conclusion of N2 Closed Circuit test (iii) Reinstallation of piping system after item (i) (iv) Check all major process variable control loops (level, temperature, pressure, minimum flow - surge) of the Compression Plant are functional. (v) Functional and logic test for all SDVs, XVs and BDVs of the Compression Plant.
36 | Topside-Gas | Gas Injection Compression | (i) N2He Leak Test packages concluded in suction, interastage, discharge. (ii) N2 Closed Circuit Coupled Run in all trains. Contractor is requested not to remove inlet / out pipes from compressor and not to remove coupling (Gear Box x Electrical Motor x Compressor) after conclusion of N2 Closed Circuit test (iii) Reinstallation of piping system after item (i) (iv) Check all major process variable control loops (level, temperature, pressure, minimum flow - surge) of the Compression Plant are functional. (v) Functional and logic test for all SDVs, XVs and BDVs of the Compression Plant.
37 | Topside-CO2 | CO2 Compression System | (i) N2He Leak Test packages concluded in suction, interastage, discharge. (ii) N2 Closed Circuit Coupled Run in all trains. Contractor is requested not to remove inlet / out pipes from compressor and not to remove coupling (Gear Box x Electrical Motor x Compressor) after conclusion of N2 Closed Circuit test (iii) Reinstallation of piping system after item (i) (iv) Check all major process variable control loops (level, temperature, pressure, minimum flow - surge) of the Compression Plant are functional. (v) Functional and logic test for all SDVs, XVs and BDVs of the Compression Plant.
38 | Topside-Gas | VRU | (i) N2He Leak Test packages concluded in suction, interastage, discharge. (ii) N2 Closed Circuit Coupled Run in all trains. Contractor is requested not to remove inlet / out pipes from compressor and not to remove coupling (Gear Box x Electrical Motor x Compressor) after conclusion of N2 Closed Circuit test (iii) Reinstallation of pipping system after item (i) (iv) Check all major process variable control loops (level, temperature, pressure, minimum flow) of the Compression Plant are functional. (v) Functional and logic test for all SDVs, XVs and BDVs of the Compression Plant.
39 | Topside-Gas | Gas Refrigeration Compression System | (i) N2He Leak Test concluded; (ii) Functional test of refrigerant compressor package. (iii) Check all major process variable control loops (level, temperature, pressure) of the System (Gas Chiller and Refrigerant Loop and Cold Separator). (iv) Functional and logic test for all SDVs, XVs and BDVs of the System.
40 | Topside-Gas | Gas Dehydration and Regeneration (Mol Sieves) | (i) N2He Leak Test concluded (ii) Functional and logic test for all Molecular Sieves inlet/outlet XVs (iii) Mol Sieve Vessels media full filling for each vessel (iv) System to be kept preserved with nitrogen. (v) Check all Gas regeneration heaters are with adequate level of isolation. (vi) Check dew point analyzer calibration (vii) Gas Heaters megger testing (viii) Compressor/blower test for mol sieve regeneration (if any)
41 | Topside-Gas | Gas Sweetening Unit - GSU (Amine) | (i) N2He Leak Test concluded (ii) Check all major process variable control loops (level, temperature, flow) of GSU (iii) Functional and logic test for all GSU XVs, SDVs and BDVs (iv) Amine inventory filling for the GSU (v) Packing (recheio, ex.: Pall Ring Packing) filling for Amine Contactor and Amine Stripper Towers. (vi) Functional test of all Amine circulation Pumps including seal system. (vii) System to be kept preserved with nitrogen. (viii) Check Amine Reboiler resistance bundle heaters (electrical resistors) are with adequate level of isolation. (ix) Check online H2S/CO2 content analyzers calibration (upstream and downstream unit of the contactor tower).
42 | Topside-Gas | Gas Dehydration Unit - GDU (TEG) | (i) N2He Leak Test concluded (ii) Check all major process variable control loops (level, temperature, flow) of GDU (iii) Functional and logic test for all GDU XVs, SDVs and BDVs (iv) TEG inventory filling for the GDU (v) Packing (recheio, ex.: Pall Ring Packing) filling for TEG Absorber column and TEG Regeneration Tower. (vi) Functional test of all TEG circulation Pumps including seal system. (vii) System to be kept preserved with nitrogen. (viii) Check TEG Reboiler resistance bundle heaters (electrical resistors) are with adequate level of isolation. (Megger check) (ix) Check online dew point (H2O content) analyzer calibration (downstream unit of the TEG absorber column).
43 | Topside-Gas | Fuel Gas | (i) Gas Heaters (import & fuel) megger testing (ii) N2He Leak Test concluded. (iii) Check all major process variable control loops (level, temperature, pressure) of the Fuel Gas System are functional. (iv) Functional and logic test for all SDVs and BDVs of the Fuel Gas System
44 | Topside-CO2 | Gas Treatment (CO2 Removal) | (i) N2He Leak Test concluded (ii Cleaness verification of all casings; (iii) Membranes cartridges loading with vendor attendance; (iv) Keep system preserved with N2 after loading; (v) Check Instruments and control valves, verify control logic sequences (vi) Check all major process variable control loops (temperature, pressure) of the CO2 Removal System are functional. (vii) Functional and logic test for all SDVs and BDVs of the CO2 Removal System
45 | Topside-gas | LP Flare Tips & Ignition Panel | (i) Visual Inspection of flare tip before ignition test; (ii) Check the flare ignition by using propane bottles and igniters; (iii) Verify auto / manual ignition, flame presence and flame failure (iv) Simulate flame out to test redundant ignition system (v) Check flow logical loops (FSL, FSLL) for the Purge gas (N2 and fuel gas). (vi) Functional and logic test for all XVs for the Purge gas and BDVs for the Flare Stages. (vii) Check control system for BDVs in case of dead ship scenario.
46 | Topside-gas | LP Flare KO Drum & Pumps | (i) Functional Test of all pumps including seal system. (ii) Check vessel instumentation (iii) N2He Leak Test Concluded. (iv) Check level control loops for the Flare Vessels.
47 | Topside-Water | Sea Water Treatment and Injection | (i) Mechanical Completion Certificate (ii) All Pumps with Motor Sollo Run, inlet/outlet pipes connected, coupling installed, Lube Oil Flushing, all hot loops concluded (iii) Vaccum Test at Dearator Tower Concluded. (iv) SRU Chemical Cleaning System Tested with water. (v) Functional test of PSV downstream interlock system for SW injection or SW+PW injection mode
48 | Topside-Water | Produced Water | (i) Functional test of PW Collection Vessel, Hydrocyclones, IGF Vessel & pumps, gas injection for flotation and PW Coolers. (ii) Functional test of all Produced Water Booster Pumps including seal system. (iii) Online TOG Analyser commissioning and operability (iv) Functional and logic test for XVs (produced water alignment to overboard or offspec tank)
49 | Subsea Interface | Subsea HPU Distribution & ESDV /WCR Panel | (i) Functional test to verify if LP and HP is working properly, and the TUTU plate alignment with no leakages (ii) Verify NAS 6 spec for the water based oil is achieved at each tutu position. (iii) Check 2 units of PUPS (Portable Umbilical Pressurization System) available on board as per GTD
50 | Subsea Interface | Riser Balcony | (i) Verify if spool required for riser leak test prior to start up are available and properly identified, stored and preserved. Riser Flange groove and faces shall have no deffects that may impose leaks; (ii) Verify all E&I interfaces (TUTU plates identification, Umbilical Junction Boxes) are in accordande with specification to avoid any interface problems during the risers hook-up activities; (iii) Check if each EJB terminal blocks is capable to accept any umbilical conductor size. Check EJB cable Glands are correct sized. (iv) Verify if all the required spools are correctly installed in accordance of the slots functions and pipe alignements in accordance with Subsea Lay-Out. (v) Check Riser Carcass Vent completion as per GTD (vi) Leak testing of lower riser balcony hard piping including hook-up spool with mock-up (rigid riser) (vii) Verification of material for riser installation: pieces of studs, nuts, gaskets
51 | Safety | Deluge (Marine and Topsides) Water | (i) Actual Water Deluge test in all fire zones (i.e. deck / balcony level etc) to check pressure and flow rates were achieved as per design and ANP requirements. (Report with measured pressure and flow data and whether they are in accordance with the project shall be available for Petrobras); (ii) Check time for deluge valve opening and nozzles spray pattern are in accordance with design; (iii) Check whether the drainage system absorbed the water discharge flow from the deluge system without causing the containments to overflow. No overflow from one zone to another or to sea shall be ensured during tests; (iv) Check the positioning of the spray nozzles according to the project; (v) Check for possible physical interference that could interfere with the application of water through the spray nozzles.
52 | Safety | Deluge (Marine andTopsides) Foam | (i) Actual Water Deluge test in all fire zones to check pressure and flow rates were achieved as per design and ANP requirements; (ii) Check time for deluge valve opening and nozzles spray pattern are in accordance with design. (iii) Report with measured pressure and flow data and whether they are in accordance with the project shall be available for Petrobras. (iv) Check the positioning and type of the spray nozzles according to the project; (v) Check correct dosage of LGE through proportioning systems, according to NFPA-11 (vi) Check LGE tank levels and laboratory and fire test certificates; (vii) Check for possible physical interference that could interfere with the application of foam through the spray nozzles. (viii) Actual Release of Foam in two fire zones to be mutually agreed with Petrobras; (ix) Check if Foam spec is met as per regulations.
53 | Safety | Fire Fighting System | (i) Local and automatic start-up and functional test of all pumps per 30 min each cause by low pressure in main ring; (ii) Verification of functionality of the hydrant at far position from the pumps and helideck monitor too; (iii) Functional test of jockey pumps, as per design requirements; (iv) Perform capacity test of all fire pumps in the installation, with flow metering to confirm system performance as per NFPA 25 (ANP requirement) and also check whether the TAFs for each pump are available; (v) Verification of the diesel tank capacity to run 18 hours continuous the fire pumps; (vi) Check that the main ring blocking valves are in the positions foreseen in the design and that they are operational (mainly the XVs); (vii) Check the PSV set point and the D58PCV set point are in accordance with the project.
54 | Safety | Portable monitors | (i) Check that the monitors are installed and intact in the provided shelters and that they are complete according to specification (base, body and nozzle); (ii) Check the capacity of the monitors according to specification;
55 | Safety | PA/GA communication system | (i) Check that the communication systems are in accordance with the project and that they are tested and approved.
56 | Safety | Emergency Shutdown and Blow Down | (i) Test of all fire push buttons (manual call points) to check are functional; (ii) Verification of the implementation of the ESD Logic according to the emergency stop diagram - Evidence; (iii) Check the Depressurization and Blocking Logic according to the Project (check the logical and mechanical timing if it has been implemented and tested) - Evidence.
57 | Safety | Safety Eye Shower | (i) Check the position of Safety Eyewash / showers that must be installed on the same floor, in a readily accessible, easy-to-locate location that does not require more than 10 (ten) seconds to be reached, counting from the risk, and in accordance with the project ; (ii) Check that the valves installed in the supply network for maintenance purposes are locked open; (iii) Check safety signs; (iv) Check that all the Safety Eyewash / shower is operational and that the nozzles are working without obstruction (on-site test).
58 | Safety | Scape Routes | (i) Check 100% scape route demarcation and signalization in accordance with the project and ensure there is no obstruction; (ii) Check compliance with the minimum dimensions of the main routes (Width 1.2 m, height 2.10) and secondary routes (Width 1.0 m, height 2.10). (iii) check emergency lighting on the scape route.
59 | Safety | Safety Plan | (i) Safety Plan As Built version fixed on the walls stamped by Classification Society (ii) Contractor shall verify position of all itens in the Safety Plan
60 | Safety | UPS | (i) UPS discharge test (ii) Function check of Static switch and bypass switch, alarms and trips. (iii) Power redundancy test for emergency loads
61 | Safety | Portable multigas detectors (CH4, H2S, O2, CO and volatile organic compounds) | (i) Check that at least two portable instruments are available on board to detect CH4, H2S, O2, CO and Volatile Organic Compounds (NR 37 item: 37.23.11); (ii) Check if there is a compatible standard gas cylinder within the validity period to carry out the detector tests.
62 | Safety | F&G (Topsides and Marine) Gas detection system (plant and air intakes) | (i) Contractor to perform functional test of all F&G sensors with actual gas. PEtrobras might witness some of these tests and Check the F&G Matrix with the automation and instrumentation discipline - Show that the logic has been tested; (ii) Check the positioning of detectors according to the project (X,Y,Z) - maximum deviation in relation to the coordinates of 0.5m in any direction; (iii) Check the line of sight of open path detectors according to the maximum deviation allowed by the manufacturer; (iv) Check whether the air intakes have gas detectors as per the project (check the quantity and type of detector provided); (v) Check for interference/obstructions - especially for sight lines; (vi) Check availability of Ex certificates for detectors; (vii) Check that the detectors are operational; (viii)Check whether the battery room has a hydrogen (H2) detection and alarm system, considering in its location the influence of the air exhaust and supply system in the compartment (item of NR 37: 37.23.15).
63 | Safety | F&G (Topsides and Marine) Fire detection system (all areas, including turbomachinery hoods) | (i) Check the F&G Matrix with the automation and instrumentation discipline - Show that the logic has been tested; (ii) Check the positioning of flame detectors according to the project (X,Y,Z / Cone viewing angle), in case of deviation consult the designer; (iii) Check the installation of fire detectors in the installation's closed areas according to the project (smoke, fixed temperature and thermovelocimetric); (iv)Check whether there are interferences/obstructions to the flame detectors; (v)Check that the detectors are operational.
64 | Safety | PFP (Passive Fire Protection) | (i) Check All PFP for structure, piping and pipe supports are 100% completed; (ii) Check all PFP jackets for Risers ESDVs, BDVs, and any other valves are 100% completed; (iii) Check the existence of documents that demonstrate correct application in accordance with the manufacturer's certificate and instructions; (iv) Check whether all structural protection, equipment supports and valves were applied according to the project (defined area, type of protection...); (v) Check the existence of certificates for all Passive Fire Protection materials and their validity;
65 | Safety | Isolation | (i) Check positive isolation for non-connected wells as per design; (ii) Check that non-operational systems on board are positively isolated and segregated from other systems;
66 | Safety | Rescue Boat and Life Boats | (i) Functional test of Rescue Boat & davits (in accordance with the LSA Code); (ii) Functional test of all life Boats - Partial Launching (in accordance with the LSA Code); (iii) Visual check no obstructions/interference of break release wires and safety pins removal with easy access; (iv) Check the quantity and capacity of the life boats according to the project; (v) Check that the launching davits have been tested according to the load testing procedure; (vi) Check whether the buoys are in the position defined in the project and whether they are certified; (vii) Check that the life jackets are in accordance with the project specifications and that the quantities are met in each defined location.
67 | Safety | CO2 & Friendly Gas Fixed Fire Supression System | (i) Actual Release of all Compartments, including galley hood supression system, to demonstrate the following: Dampers close check; No obstructions in any CO2 or Inergen (or similar) nozzles; CO2 /O2 (in case of Inergen or similar gas) concentration and time critera achieved as per NFPA; Compartment integrity check after test; Check ventilation stop signal, pre-discharge alarm and release time delay. Obs: Check in the system acceptance test report for each compartment whether it was carried out with CO2 and whether the system was approved and shall be made available for PETROBRAS;
68 | Safety | Water mist system | (i) Actual Release of Deluge System (ii) Check that visual and audible safety signs and warning signs for protected rooms are installed (on the doors on the external side and inside the room).
69 | Safety | Riser ESDV and BDV Valves | (i) Functional test of all riser ESDVs valves at riser balcony area to check opening/closing time; (ii) Check ESDV valve tightness . Reports to be made available to Petrobras. (iii) Functional test of all BDV (spot check).
70 | Marine | Positioning Reference System | (i) Visual verification of all system and check if there is some obstructions on the antenas used for communication between the FPSOs and DPST; (ii) Check if the measurement of the antenna (DARPS, ARTEMIS and FANBEAM) positions used in the offloading was carried out
71 | Topside-gas | Flare Gas Recovery System | (i) N2He Leak Test packages concluded in suction and discharge pipes. (ii) N2 / Open Air Coupled Run or Air Running in compressors. (iv) Check all major process variable control loops (level, temperature, pressure, minimum flow - surge) of the Compression Plant are functional. (v) Quick Opening Valves functional tests including logic / signals (Pressure Transmitters, etc). (vi) Functional check of Nitrogen Generators (including supply)
Note: For exceptional cases, Buyer, under its sole discretion, may waive partially the scope of Appendix 1 based on justification presented by Seller.