## EXHIBIT XI - APPENDIX 1
EXHIBIT XI - APPENDIX 1 - Price Schedule “A” with Advanced Payment and Price Schedule “B” and Price Schedule "C"
***********Revision Control*********** 0: Original version
P-91 - SCHEDULE A
Item on Exhibit XI | Milestone | % Absolut
% Total |  | 100%
5.1 | Engineering | 5.5%
5.1.1 | Submission of Risk and Safety Studies | 0.6%
5.1.2 | Hull Global and Fatigue Analysis | 0.3%
5.1.3 | Design Review (30%) | 2%
5.1.4 | Submission of the Pipe Stress Analysis (90%) and related isometrics | 0.3%
5.1.5 | Approved for Construction P&Ids (90%) | 0.2%
5.1.6 | Design Review (60%) | 1%
5.1.7 | Design Review (90%) and Delivery of the CAE Tools Database (75%) | 0.7%
5.1.8 | As-built design and Delivery of the CAE Tool Database (100%) | 0.4%
5.2 | Acquisitions | 41.2%
5.2.1 | Purchase order (PO) for 50% of Structure Steel (Design Review minimum progress 60%) | 1.5%
5.2.2 | Purchase order (PO) for 80% and delivery for 40% of Structure Steel (Design Review minimum progress 90%) | 1.5%
5.2.3 | Purchase order (PO) for 90% and delivery for 80% of Structure Steel (Design Review minimum progress 90%) | 1.5%
5.2.4 | Purchase order (PO) for 50% of Piping (Design Review minimum progress 60%) | 1.5%
5.2.5 | Purchase order (PO) for 80% and delivery for 40% of Piping (Design Review minimum progress 90%) | 1.5%
5.2.6 | Purchase order (PO) for 90% and delivery for 80% of Piping (Design Review minimum progress 90%) | 2.5%
5.2.7 | Purchase Order (PO) of the Main Power Generators packages | 0.5%
5.2.8 | Receipt of Electric Generators and start of Main Equipment installation on skid of Main Power Generators packages | 1.5%
5.2.9 | Delivery of Main Power Generators packages | 3%
5.2.10 | Purchase Order (PO) for Gas Compressors packages | 0.5%
5.2.11 | Receipt of Electric Motor and HVSD for Gas Compressors packages (Main, Export and VRU Services) | 1.4%
5.2.12 | Delivery of Gas Compressors packages (Main, Export and VRU Services) | 3%
5.2.13 | Receipt of Electric Motor and HVSD for Gas Injection Compressors packages | 1%
5.2.14 | Delivery of Gas Injection Compressors packages | 1.5%
5.2.15 | Receipt of Electric Motor and HVSD for CO2 Gas Compressors packages | 1%
5.2.16 | Delivery of CO2 Gas Compressors packages | 1.5%
5.2.17 | Purchase Order (PO) for Sea Water Lift Pumps, Water Injection Pumps and Water Treatment Unit | 0.4%
5.2.18 | Delivery of Sea Water Lift Pumps, Water Injection Pumps and Water Treatment Unit | 2%
5.2.19 | Purchase Order (PO) for Oil Separators and Electrostatic Treaters | 0.4%
5.2.20 | Delivery of Oil Separators and Electrostatic Treaters | 2%
5.2.21 | Purchase Order (PO) for CO2 removal unit, H2S removal unit and TEG (Triethylene Glycol) unit | 0.5%
5.2.22 | Delivery of CO2 removal unit, H2S removal unit and TEG (Triethylene Glycol) unit | 1%
5.2.23 | Purchase Order (PO) for Hull Auxiliary and Emergency Power Generators and Unit Fire Fighting Pumps | 0.4%
5.2.24 | Receipt of Diesel Engine and Hydraulic Power Pack for Hull Auxiliary and Emergency Power Generators and Unit Fire Fighting Pumps | 2%
5.2.25 | Delivery of Hull Auxiliary and Emergency Power Generators and Unit Fire Fighting Pumps | 2.1%
5.2.26 | Purchase Order (PO) for Hull Engine Room Main equipment | 1%
5.2.27 | Delivery of Hull Engine Room Main equipment | 2%
5.2.28 | Purchase Order (PO) of Unit's Mooring, Fixed Boom Cranes and Pull-in Systems | 1%
5.2.29 | Delivery of Unit's Mooring, Fixed Boom Cranes and Pull-in package | 1.5%
5.3 | Hull | 13.5%
5.3.1 | Strike Steel | 0.5%
5.3.2 | Keel Laying | 2%
5.3.3 | Blocks erection (25%) | 2%
5.3.4 | Blocks erection (50%) | 2%
5.3.5 | Blocks erection (75%) | 1%
5.3.6 | Engine Room Main Equipment | 0.6%
5.3.7 | Forecastle Main Equipment | 0.6%
5.3.8 | Hull Piping Reinstatement Folders Acceptance (50%) | 0.6%
5.3.9 | Hull Systems MCC (30%) | 0.9%
5.3.10 | Hull Systems MCC (60%) | 0.9%
5.3.11 | Hull Systems MCC (90%) | 0.6%
5.3.12 | Hull Areas/Compartment Completion (90%) | 0.3%
5.3.13 | Load Test of Hull Generators | 0.5%
5.3.14 | Performance Tests of main Hull Systems | 0.5%
5.3.15 | Hull Completion | 0.5%
5.4 | Topside | 10.9%
5.4.1 | Finish “pancake” fabrication for Power Generation and Electric/Automation Modules | 0.1%
5.4.2 | Finish “pancake” fabrication for Compression Modules | 0.1%
5.4.3 | Finish “pancake” fabrication for the other Modules | 1%
5.4.4 | Power Generation Modules fabrication - Main equipment | 1%
5.4.5 | Compression Modules fabrication - Main equipment | 1%
5.4.6 | Power Generation Modules Completion | 1.5%
5.4.7 | Oil Treatment Modules Completion | 1%
5.4.8 | Gas Treatment Modules Completion | 1%
5.4.9 | Utilities and Electric/Automation Module(s) Completion | 1%
5.4.10 | Other Unit Modules Completion | 1%
5.4.11 | Compression Modules Completion | 1%
5.4.12 | Lifting of the First Topsides Module | 0.7%
5.4.13 | Lifting of the last Topsides Module | 0.5%
5.5 | Integration | 13.9%
5.5.1 | Habitability | 0.7%
5.5.2 | Hook-up - Integration Piping Reinstatement (50%) | 3%
5.5.3 | On-shore Full Load Test | 3%
5.5.4 | On-shore Plant Simulation | 1%
5.5.5 | On-shore N2He Leak Test (90%) | 1%
5.5.6 | Onshore Scope Preliminary Acceptance Certificate | 1%
5.5.7 | On-shore Gas Compression and Injection Systems testing | 1%
5.5.8 | Implement of Risk Assessment and Safety Studies | 0.6%
5.5.9 | Substantial Completion | 1.6%
5.5.10 | Unit Handover | 1%
5.6 | Acceptance | 5%
5.6.1 | Ready for oil production | 0.6%
5.6.2 | Ready for water injection | 0.5%
5.6.3 | Ready for Flare-out | 0.5%
5.6.4 | Continuous operation test of oil production and treatment plant | 0.5%
5.6.5 | Continuous complete offloading operation (bow and stern station) | 0.2%
5.6.6 | Continuous operation test of gas treatment and compression plants | 0.5%
5.6.7 | Continuous operation test of sea water treatment and injection plants | 0.3%
5.6.8 | Continuous operation test of produced water treatment and disposal and water injection plants | 0.3%
5.6.9 | Not Applicable | 0%
5.6.10 | Continuous operation test of other systems and plants (only Systems that can only be tested offshore, due to operating conditions and process fluid) | 0.45%
5.6.11 | Unit Final Completion | 0.9%
5.6.12 | Unit Final Acceptance | 0.25%
5.7 | Advance Payment | 10%
P-91 - SCHEDULE B
Item on Exhibit XI | Milestone | % Absolut
% Total |  | 100%
6.1 | Schedule B Additional Items (Operational Spare Parts; Capital Spares and Special Tools Stored On Shore) | 100%
6.1.x | Equipment delivered. To be broken down according to Seller proposal and approved by Buyer | xx,xx%
P-91 - SCHEDULE C
Item on Exhibit XI | Milestone | % Absolut
% Total |  | 100%
7.1 | Mooring Components | 100%
7.1.x | Equipment delivered in the totality of the items. | xx,xx%